## Dashboard
GIT AUDIT REPORT — SOFTWARE CI STATUS DASHBOARD
Generated: February 2026 ¦ Total CIs Tracked: 545 ¦ Teams: 5
Total CIs |  |  |  | Git Available |  |  |  | Git Not Available |  |  | Git Adoption % | Teams Tracked
545 |  |  |  | 445 |  |  |  | 100 |  |  | 81.7% | 5
TEAM-WISE GIT ADOPTION SUMMARY
Team | Total CIs | Git Available | Git Not Available | Adoption % | Completed | In Progress | On Hold | Other | Total Pushes | Unique Products
AGM | 71 | 55 | 16 | 77.5% | 4 | 10 | 1 | 56 | 283 | 30
Application | 217 | 182 | 35 | 83.9% | 84 | 72 | 16 | 45 | 2710 | 90
BSP | 72 | 43 | 29 | 59.7% | 5 | 51 | 11 | 5 | 428 | 31
Computing | 99 | 92 | 7 | 92.9% | 4 | 14 | 2 | 79 | 506 | 25
RAD | 86 | 73 | 13 | 84.9% | 13 | 8 | 10 | 55 | 1305 | 25
TOTAL | 545 | 445 | 100 | 81.7% | 110 | 155 | 40 | 240 | 5232 | 201

## Charts & Analysis
GIT AUDIT — CHARTS & VISUAL ANALYSIS
Chart 1: Git Availability by Team
Team | Git Available | Git Not Available
AGM | 55 | 16
Application | 182 | 35
BSP | 43 | 29
Computing | 92 | 7
RAD | 73 | 13
Chart 2: CI Status Distribution by Team
Team | Completed | In Progress | On Hold | Other
AGM | 4 | 10 | 1 | 56
Application | 84 | 72 | 16 | 45
BSP | 5 | 51 | 11 | 5
Computing | 4 | 14 | 2 | 79
RAD | 13 | 8 | 10 | 55
Chart 3: Overall Git Availability
Status | Count
Git Available | 445
Git Not Available | 100

## Full CI Data
Sl.No | Project ID | Product ID | Software Product (CI) | In-Charge | Product Status | Status | Total Push Count | First Push Date | Last Push Date | Duration (days) | Git Availability | Observations | Team
1 | YIA2822_FCR_MIG29-K1 | DP-VPX-0224 | DP-VPX-0224-V1-01-BRAM-LIBS-ARM-LIN5V10 | Vishnu | Testing Stage | SETUP UNAVAILABLE | 2 | 2025-11-07 | 2025-11-07 | 0 | Available |  | Computing
2 |  |  | DP-VPX-0224-V1-01-PL-LIBS-ARM-LIN5V10 |  |  |  | 2 | 2025-11-07 | 2025-11-07 | 0 | Available |  | Computing
3 |  |  | DP-VPX-0224-V1-01-PLL-LIBS-ARM-LIN5V10 |  |  |  | 2 | 2025-11-07 | 2025-11-07 | 0 | Available |  | Computing
4 |  |  | DP-VPX-0224-V1-01-PS-LIBS-ARM-LIN5V10 |  |  |  | 2 | 2025-11-07 | 2025-11-07 | 0 | Available |  | Computing
5 |  |  | DP-VPX-0224-V1-01-RF-LIBS-ARM-LIN5V10 |  |  |  | 2 | 2025-11-07 | 2025-11-07 | 0 | Available |  | Computing
6 |  |  | DP-VPX-0224-V1-01-RFDC-LIBS-ARM-LIN5V10 |  |  |  | 2 | 2025-11-07 | 2025-11-07 | 0 | Available |  | Computing
7 |  |  | DP-VPX-0224-V1-01-AS-ARM-LIN5V10 |  |  |  | 7 | 2025-07-25 | 2025-11-07 | 105 | Available |  | Computing
8 |  |  | DP-VPX-0224-V1-01-AS-X86-W10 |  |  |  | 4 | 2025-07-25 | 2025-11-07 | 105 | Available |  | Computing
9 |  |  | DP-VPX-0224-V1-01-DS-ARM-LIN5V10 |  |  |  | 6 | 2025-07-25 | 2025-11-07 | 105 | Available |  | Computing
10 |  | DP-VPX-0227 | DP-VPX-0227-V1-01-AS-ATP-ARM-LIN5V04 |  | Testing Stage | QAC | 8 | 2025-07-25 | 2025-11-13 | 111 | Available |  | Computing
11 |  |  | DP-VPX-0227-V1-01-AS-AUTOMATION-ARM-LIN5V04 |  |  |  | 2 | 2025-07-25 | 2025-09-01 | 38 | Available |  | Computing
12 |  |  | DP-VPX-0227-V1-01-AS-HSDC-AUTO-X86-W10-1V00 |  |  |  | 2 | 2025-07-25 | 2025-09-01 | 38 | Available |  | Computing
13 |  |  | DP-VPX-0227-V1-01-DS-ARM-LIN5V04 |  |  |  | 2 | 2025-07-25 | 2025-09-01 | 38 | Available |  | Computing
14 |  |  | DP-VPX-0227-V1-01-LIBS-ARM-LIN5V04 |  |  |  | 7 | 2025-07-25 | 2025-11-13 | 111 | Available |  | Computing
15 |  | DP-VPX-2003 | DP-VPX-2003-V1-01-AS-ARM-LIN5V10 |  | Testing Stage | ON HOLD | 20 | 2025-07-25 | 2026-02-02 | 192 | Available |  | Computing
16 |  |  | DP-VPX-2003-V1-01-DS-ARM-LIN5V10 |  |  |  | 9 | 2025-07-25 | 2026-02-02 | 192 | Available |  | Computing
17 |  |  | DP-VPX-2003-V1-01-LIBS-ARM-LIN5V10 |  |  |  | 8 | 2025-07-25 | 2026-02-02 | 192 | Available |  | Computing
18 |  | DP-VPX-5792 | DP-VPX-5792-V1-01-AS-PPC-LIN4V20 |  | Testing Stage | UNDER PROGRESS | 6 | 2025-07-25 | 2025-11-14 | 112 | Available |  | Computing
19 |  |  | DP-VPX-5792-V1-01-DS-PPC-LIN4V20 |  |  |  | 11 | 2025-07-25 | 2025-12-17 | 145 | Available |  | Computing
20 |  |  | DP-VPX-5792-V1-01-LIBS-PPC-LIN4V20 |  |  |  | 11 | 2025-07-25 | 2025-11-27 | 125 | Available |  | Computing
21 |  | DP-VPX-7154 | DP-VPX-7154-V1-01-AS-W10 | Shiva Parvathi | Requirement Stage | UNDER PROGRESS | 2 | 2026-01-28 | 2026-01-28 | 0 | Available |  | Computing
22 | YEA2876 | DP-SPL-0244 | DP-SPL-0244-600-V1-01-AS-ARM-LIN6V12 | Narendra | Testing Stage | ON HOLD | 3 | 2025-11-13 | 2025-11-13 | 0 | Available |  | Computing
23 |  |  | DP-SPL-0244-600-V1-01-AS-X86_64-W10 |  |  |  | 1 | 2025-11-13 | 2025-11-13 | 0 | Available |  | Computing
24 |  |  | DP-SPL-0244-600-V1-01-LIBS-X86_64-W10 |  |  |  | 1 | 2025-11-13 | 2025-11-13 | 0 | Available |  | Computing
25 |  |  | DP-SPL-0244-660-V1-01-LIBS-ARM-LIN6V12 |  |  |  | 8 | 2025-11-13 | 2025-11-18 | 5 | Available |  | Computing
26 |  | DP-DSP-8208 | DP-DSP-8208-660-V1-01-AS-ARM-LIN6V12 |  | Testing Stage | UNDER PROGRESS | 9 | 2025-11-13 | 2026-02-05 | 84 | Available |  | Computing
27 |  |  | DP-DSP-8208-660-V1-01-AS-X86_64-W10 |  |  |  | 8 | 2025-11-13 | 2026-02-05 | 84 | Available |  | Computing
28 |  |  | DP-DSP-8208-660-V1-01-LIBS-ARM-LIN6V12 |  |  |  | 4 | 2025-11-13 | 2025-12-04 | 21 | Available |  | Computing
29 |  |  | DP-DSP-8208-660-V1-01-LIBS-X86_64-W10 |  |  |  | 1 | 2025-11-13 | 2025-11-13 | 0 | Available |  | Computing
30 | YEB2935 | DP-VPX-0233 | DP-VPX-0233 | Gowthami | Testing Stage | QAC | 4 | 2026-01-12 | 2026-01-13 | 1 | Available |  | Computing
31 |  |  | DP-VPX-0233-V1-01-AS-ATP-ARM-LIN5V04 |  |  |  | 8 | 2025-07-25 | 2025-11-18 | 116 | Available |  | Computing
32 |  |  | DP-VPX-0233-V1-01-AS-AUTOMATION-ARM-LIN5V04 |  |  |  | 6 | 2025-07-25 | 2025-11-10 | 108 | Available |  | Computing
33 |  |  | DP-VPX-0233-V1-01-AS-HSDC-AUTO-X86-W10 |  |  |  | 8 | 2025-07-25 | 2025-11-10 | 108 | Available |  | Computing
34 |  |  | DP-VPX-0233-V1-01-DS-ARM-LIN5V04 |  |  |  | 6 | 2025-07-25 | 2025-11-10 | 108 | Available |  | Computing
35 |  |  | DP-VPX-0233-V1-01-LIBS-ARM-LIN5V04 |  |  |  | 8 | 2025-07-25 | 2025-11-07 | 105 | Available |  | Computing
36 | YEA2918 | DP-OBC-8178 | DP-OBC-8178-663-V1-01-AS-ARINC615A-DL-X86_64-LIN5V14 | Mohamed Ali | Customer Test/Response | COMPLETED | 4 | 2025-08-11 | 2025-08-13 | 2 | Available |  | Computing
37 |  |  | DP-OBC-8178-663-V1-01-AS-ARINC615A-THW-X86_64-LIN5V14 |  |  |  | 3 | 2025-08-11 | 2025-08-13 | 2 | Available |  | Computing
38 |  |  | DP-OBC-8178-663-V1-01-AS-SIM-SU-X86-W10 |  |  |  | 3 | 2025-11-20 | 2025-11-20 | 0 | Available |  | Computing
39 |  |  | DP-OBC-8178-663-V1-01-AS-SIM-PU-X86-W10 |  |  |  | 5 | 2025-08-11 | 2026-01-07 | 149 | Available |  | Computing
40 |  |  | DP-OBC-8178-663-V1-01-AS-TTMB1-X86_64-LIN5V14 |  |  |  | 17 | 2025-08-11 | 2025-12-24 | 135 | Available |  | Computing
41 |  |  | DP-OBC-8178-663-V1-01-AS-TTMB2-X86_64-LIN5V14 |  |  |  | 11 | 2025-08-11 | 2025-12-24 | 135 | Available |  | Computing
42 |  |  | DP-OBC-8178-663-V1-01-DS-X86_64-LIN5V14 |  |  |  | 1 | 2025-08-11 | 2025-08-11 | 0 | Available |  | Computing
43 |  |  | DP-OBC-8178-663-V1-01-LIBS-ARINC615A-X86_64-LIN5V14 |  |  |  | 2 | 2025-08-11 | 2025-08-13 | 2 | Available |  | Computing
44 |  |  | DP-OBC-8178-663-V1-01-LIBS-X86_64-LIN5V14 |  |  |  | 1 | 2025-08-11 | 2025-08-11 | 0 | Available |  | Computing
45 |  |  | DP-OBC-8178-V1-02-LIB-LINUX-OS |  |  |  | 35 | 2025-06-04 | 2026-01-09 | 219 | Available |  | Computing
46 |  |  | DP-OBC-8178-V1-02-US-LINUX |  |  |  | 12 | 2025-06-12 | 2025-10-29 | 139 | Available |  | Computing
47 | YEC2874 | DP-SPL-0238 | DP-SPL-0238-V1-01-AS-X86-W10 | Hafeez | Testing Stage | SETUP UNAVAILABLE | 17 | 2025-08-11 | 2026-02-04 | 177 | Available |  | Computing
48 |  |  | DP-SPL-0238-V1-01-FWS-ARM-NOS |  |  |  | 6 | 2025-08-11 | 2025-11-10 | 91 | Available |  | Computing
49 |  |  | DP-SPL-0238-V1-01-IS-X86-W10 |  |  |  | 1 | 2025-11-06 | 2025-11-06 | 0 | Available |  | Computing
50 |  |  | DP-SPL-0238-V1-01-LIBS-ARM-NOS |  |  |  | 14 | 2025-08-11 | 2025-11-10 | 91 | Available |  | Computing
51 | YIA2927 | DP-VPX-0236 | DP-VPX-0236-V1-01-AS-ATP-ARM-LIN5V10 | Gowthami | Testing Stage | UNDER PROGRESS | 7 | 2025-11-06 | 2025-12-02 | 26 | Available |  | Computing
52 |  |  | DP-VPX-0236-V1-01-AS-AUTOMATION-ARM-LIN5V10 |  |  |  | 9 | 2025-11-06 | 2025-12-02 | 26 | Available |  | Computing
53 |  |  | DP-VPX-0236-V1-01-AS-HSDC-AUTO-X86-W10 |  |  |  | 4 | 2025-07-25 | 2025-11-10 | 108 | Available |  | Computing
54 |  |  | DP-VPX-0236-V1-01-DS-ARM-LIN5V10 |  |  |  | 6 | 2025-11-06 | 2025-11-10 | 4 | Available |  | Computing
55 |  |  | DP-VPX-0236-V1-01-LIBS-ARM-LIN5V10 |  |  |  | 7 | 2025-11-06 | 2025-12-02 | 26 | Available |  | Computing
56 |  | DP-VPX-2606 | DP-VPX-2606-V1-01-AS-ARM-LIN5V10 | Shiva Parvathi | Testing Stage | UNDER PROGRESS | 7 | 2025-09-02 | 2025-12-10 | 99 | Available |  | Computing
57 |  |  | DP-VPX-2606-V1-01-DS-ARM-LIN5V10 |  |  |  | 6 | 2025-09-02 | 2025-12-30 | 119 | Available |  | Computing
58 |  |  | DP-VPX-2606-V1-01-LIBS-ARM-LIN5V10 |  |  |  | 5 | 2025-09-02 | 2025-12-10 | 99 | Available |  | Computing
59 | YEA2936 | DP-XMC-5049 | DP-XMC-5049-V1-01-AS-X86_64-LIN5V14 | Kaushik | Testing Stage | UNDER PROGRESS | 4 | 2025-07-25 | 2026-02-04 | 194 | Available |  | Computing
60 |  |  | DP-XMC-5049-V1-01-AS-X86_64-WIN10 |  |  |  | 8 | 2025-07-25 | 2026-02-04 | 194 | Available |  | Computing
61 |  |  | DP-XMC-5049-V1-01-DS-X86_64-LIN5V14 |  |  |  | 3 | 2025-07-25 | 2025-10-01 | 68 | Available |  | Computing
62 |  |  | DP-XMC-5049-V1-01-FWS-SAMD51 |  |  |  | 12 | 2025-07-25 | 2026-01-02 | 161 | Available |  | Computing
63 |  |  | DP-XMC-5049-V1-01-LIBS-X86_64-LIN5V14 |  |  |  | 5 | 2025-07-25 | 2026-02-04 | 194 | Available |  | Computing
64 | YEC2826 | DP-VPX-1031 | DP-VPX-1031-V1-01-AS-PPC-LINUX-1V00 | Sriram | Implementation Stage | COMPLETED | 2 | 2025-12-12 | 2025-12-12 | 0 | Available |  | Computing
65 |  |  | DP-VPX-1031-V1-01-DS-PPC-LINUX-1V00 |  |  |  | 4 | 2025-12-12 | 2026-01-08 | 27 | Available |  | Computing
66 |  |  | DP-VPX-1031-V1-01-LIBS-PPC-LINUX-1V00 |  |  |  | 2 | 2025-12-12 | 2025-12-15 | 3 | Available |  | Computing
67 |  |  | DP-VPX-1031-V1-01-US-PPC-LINUX-1V00 |  |  |  | 2 | 2025-12-12 | 2025-12-15 | 3 | Available |  | Computing
68 | YEA2960 | DP-OBC-8196 | DP-OBC-8196-V1-01-AS-X86-W10 | Hafeez | Testing Stage | SETUP UNAVAILABLE | 9 | 2025-08-28 | 2025-12-09 | 103 | Available |  | Computing
69 |  |  | DP-OBC-8196-V1-01-IS-X86-W10 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
70 |  | DP-VPX-0500 | DP-VPX-0500-66033-V1-01-AS-ISBC-x86-LIN5V14 | Shahin | Implementation Stage | SETUP UNAVAILABLE | 4 | 2025-08-28 | 2025-10-28 | 61 | Available |  | Computing
71 |  |  | DP-VPX-0500-66033-V1-01-AS-ISBC-X86-W10 |  |  |  | 10 | 2025-08-28 | 2026-02-04 | 160 | Available |  | Computing
72 |  |  | DP-VPX-0500-66033-V1-01-DS-ISBC-x86-LIN5V14 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
73 |  |  | DP-VPX-0500-66033-V1-01-IS-ISBC-X86-W10 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
74 |  |  | DP-VPX-0500-66033-V1-01-LIBS-ISBC-x86-LIN5V14 |  |  |  | 5 | 2025-08-28 | 2025-09-30 | 33 | Available |  | Computing
75 |  |  | DP-VPX-0500-66300-V1-01-AS-NSBC-x86-LIN5V14 |  |  |  | 3 | 2025-08-28 | 2025-10-01 | 34 | Available |  | Computing
76 |  |  | DP-VPX-0500-66300-V1-01-AS-NSBC-X86-W10 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
77 |  |  | DP-VPX-0500-66300-V1-01-DS-NSBC-x86-LIN5V14 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
78 |  |  | DP-VPX-0500-66300-V1-01-IS-NSBC-X86-W10 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
79 |  |  | DP-VPX-0500-66300-V1-01-LIBS-NSBC-x86-LIN5V14 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
80 |  | DP-VPX-5291 | DP-VPX-5291-V1-01-AS-ARM-LIN6V6 |  | Implementation Stage | SETUP UNAVAILABLE | 2 | 2025-08-28 | 2026-01-06 | 131 | Available |  | Computing
81 |  |  | DP-VPX-5291-V1-01-AS-X86-W10 |  |  |  | 6 | 2025-08-28 | 2026-01-06 | 131 | Available |  | Computing
82 |  |  | DP-VPX-5291-V1-01-DS-ARM-LIN6V6 |  |  |  | 2 | 2025-08-28 | 2026-01-05 | 130 | Available |  | Computing
83 |  |  | DP-VPX-5291-V1-01-IS-X86-W10 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
84 |  |  | DP-VPX-5291-V1-01-LIBS-ARM-LIN6V6 |  |  |  | 3 | 2025-08-28 | 2026-01-06 | 131 | Available |  | Computing
85 |  |  | DP-VPX-5291-V1-01-OSS-ARM-LIN6V6 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
86 |  | DP-VPX-6025 | DP-VPX-6025-V1-01-AS-ARM-LIN6V6 |  | Implementation Stage | SETUP UNAVAILABLE | 8 | 2025-08-28 | 2026-01-06 | 131 | Available |  | Computing
87 |  |  | DP-VPX-6025-V1-01-AS-X86-W10 |  |  |  | 10 | 2025-08-28 | 2026-02-06 | 162 | Available |  | Computing
88 |  |  | DP-VPX-6025-V1-01-DS-ARM-LIN6V6 |  |  |  | 4 | 2025-08-28 | 2025-12-29 | 123 | Available |  | Computing
89 |  |  | DP-VPX-6025-V1-01-IS-X86-W10 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
90 |  |  | DP-VPX-6025-V1-01-LIBS-ARM-LIN6V6 |  |  |  | 8 | 2025-08-28 | 2026-01-02 | 127 | Available |  | Computing
91 |  |  | DP-VPX-6025-V1-01-OSS-ARM-LIN6V6 |  |  |  | 1 | 2025-08-28 | 2025-08-28 | 0 | Available |  | Computing
92 |  | DP-ATE-8486 | DP-ATE-8486 | Shahin | Requirement Stage | UNDER PROGRESS | 0 | - | - |  | Not Available |  | Computing
93 | YEB3037 | DP-OBC-8211 | - | - | Requirement Stage | UNDER PROGRESS | 0 | - | - |  | Not Available |  | Computing
94 |  | DP-SPL-0502 | - | - | Requirement Stage | UNDER PROGRESS | 0 | - | - |  | Not Available |  | Computing
95 | YIB2890 | DP-SPL-0241 | - | - | Requirement Stage | UNDER PROGRESS | 0 | - | - |  | Not Available |  | Computing
96 | YEB2986 | DP-XMC-6003 | - | - | Requirement Stage | UNDER PROGRESS | 0 | - | - |  | Not Available |  | Computing
97 | YEB2854 | IRST V2 | - | Mohamed Ali | Requirement Stage | UNDER PROGRESS | 0 | - | - |  | Not Available |  | Computing
98 | YEC2768 | - | - | - | Completed | Completed | 0 | - | - |  | Not Available |  | Computing
99 | YEB2800 | DP-SPL-4309 | DP-SPL-4309 | - | Completed | Completed | 4 | 2025-04-15 | 2025-06-05 | 51 | Available |  | Computing
100 | YEA2722 | DP-ADSB-8009 | CMS_DISPLAY_CLIENT | Sankardhayalsharma | Testing Stage | SITE Support | 22 | 2024-12-26 | 2026-02-13 | 414 | Available |  | RAD
101 |  |  | CMS_DISPLAY_SERVER |  |  |  | 17 | 2024-12-27 | 2025-02-12 | 47 | Available |  | RAD
102 |  |  | CMS_SERVER |  |  |  | 47 | 2024-12-28 | 2025-11-07 | 314 | Available |  | RAD
103 |  |  | DATA_PROCESSOR |  |  |  | 58 | 2024-12-29 | 2026-01-25 | 392 | Available |  | RAD
104 |  |  | SPU_A |  | Completed | Completed | 9 | 2024-12-30 | 2025-03-24 | 84 | Available |  | RAD
105 |  |  | SPU_B |  |  |  | 10 | 2024-12-31 | 2025-02-05 | 36 | Available |  | RAD
106 | YIA2819 | DP-IFF-8023 | DP-IFF-8023-INT-GUI |  | Testing Stage | QC testing | 71 | 2025-01-01 | 2026-02-12 | 407 | Available |  | RAD
107 |  |  | DP-IFF-8023-TXP-GUI |  | Testing Completed |  | 42 | 2025-01-02 | 2026-01-20 | 383 | Available |  | RAD
108 |  |  | DP-IFF-8023_APP |  | Testing Stage |  | 113 | 2025-01-03 | 2026-02-11 | 404 | Available |  | RAD
109 | YIA2749 | DP-RDR-7456 | Manpad |  | Completed | Completed | 0 |  |  | 0 | Not Available |  | RAD
110 |  | DP-RDR-7465 | SEARCH_ATP | Parthiban | Completed | Completed | 7 | 2024-12-26 | 2025-03-28 | 92 | Available |  | RAD
111 |  | DP-RDR-8227 | TRACK_ATP |  | Completed | Completed | 1 | 2024-12-26 | 2024-12-26 | 0 | Available |  | RAD
112 |  |  | EOS_VPA |  | Testing Stage | Hold | 21 | 2024-12-26 | 2025-11-20 | 329 | Available |  | RAD
113 |  |  | FCCA |  | Testing Stage | Hold | 29 | 2024-12-26 | 2026-02-12 | 413 | Available |  | RAD
114 |  |  | FCD |  | Testing Stage | Hold | 27 | 2024-12-26 | 2026-01-31 | 401 | Available |  | RAD
115 |  |  | FCD_RCT |  | Testing Stage | Hold | 2 | 2024-12-26 | 2025-01-07 | 12 | Available |  | RAD
116 |  |  | GCD |  | Testing Stage | Hold | 19 | 2024-12-26 | 2025-11-11 | 320 | Available |  | RAD
117 |  |  | GCD_RCT |  | Testing Stage | Hold | 10 | 2024-12-26 | 2025-11-11 | 320 | Available |  | RAD
118 |  |  | SIMULATOR |  | Testing Stage | Hold | 17 | 2024-12-26 | 2026-02-06 | 407 | Available |  | RAD
119 |  |  | SRCA |  | Testing Stage | Hold | 8 | 2025-11-11 | 2026-02-11 | 92 | Available |  | RAD
120 |  |  | SRSP |  | Testing Stage | Hold | 11 | 2025-08-06 | 2025-11-11 | 97 | Available |  | RAD
121 |  |  | TRCA |  | Testing Stage | Hold | 62 | 2024-12-26 | 2025-12-19 | 358 | Available |  | RAD
122 | sib2484 | DP-SWR-8002 | RDPS_WebPhp | Kannan & valeti.sanjay | Implementation on going | Implementation | 20 | 2024-12-30 | 2025-06-16 | 168 | Available |  | RAD
123 |  |  | ClientXml |  |  |  | 7 | 2026-02-11 | 2026-02-12 | 1 | Available |  | RAD
124 |  |  | Server |  |  |  | 8 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
125 |  |  | CLIENT |  |  |  | 48 | 2024-12-30 | 2025-09-29 | 273 | Available |  | RAD
126 |  |  | SERVER |  |  |  | 12 | 2024-12-30 | 2025-02-22 | 54 | Available |  | RAD
127 |  |  | AWPD |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
128 |  |  | HCA |  |  |  | 4 | 2025-11-12 | 2026-02-11 | 91 | Available |  | RAD
129 |  |  | UWT |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
130 |  |  | VAD |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
131 |  |  | VVP |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
132 |  |  | PAC |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
133 |  |  | SRI |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
134 |  |  | VIL |  |  |  | 4 | 2026-02-11 | 2026-02-11 | 0 | Available |  | RAD
135 |  |  | HDA |  |  |  | 1 | 2025-11-12 | 2025-11-12 | 0 | Available |  | RAD
136 |  |  | CAPPI |  |  |  | 17 | 2025-11-12 | 2026-02-11 | 91 | Available |  | RAD
137 |  |  | ECHO |  |  |  | 5 | 2025-11-12 | 2026-02-11 | 91 | Available |  | RAD
138 |  |  | MAX |  |  |  | 6 | 2025-11-12 | 2026-02-11 | 91 | Available |  | RAD
139 |  |  | 3DS |  |  |  | 13 | 2025-11-11 | 2026-02-11 | 92 | Available |  | RAD
140 |  |  | VHL |  |  |  | 8 | 2025-11-11 | 2026-02-11 | 92 | Available |  | RAD
141 | YEA2915 | DP-RDR-8329 | - | Baskar | Design Stage | Design | 0 | - | - |  | Not available |  | RAD
142 | YEA2930 | DP-SAR-8007 | - |  | Requirement Stage | Requirement | 0 | - | - |  | Not available |  | RAD
143 |  | DP-ATE-8432 | - |  |  |  | 0 | - | - |  | Not available |  | RAD
144 | YEA2936 | DP-RDR-8308 | - |  | Requirement Stage | Requirement | 0 | - | - |  | Not available |  | RAD
145 |  | DP-RDR-7570 | - |  |  |  | 0 | - | - |  | Not available |  | RAD
146 | YEC2826 | DP-RDR-7495 | - |  | Implementation Just Started | Implementation | 0 |  |  | 0 | Not available |  | RAD
147 |  | DP-RDR-8266 | - |  |  |  | 0 |  |  | 0 | Not available |  | RAD
148 | YIA2871 | DP-SAR-8004 | - |  | Implementation Just Started | Implementation | 0 |  |  | 0 | Not available |  | RAD
149 | YEB2830 | DP-RDR-7277 | DP-RDR-7277-V1-AS-PPC-LIN3V8 |  | Completed | Completed | 6 | 2025-05-23 | 2025-06-09 | 17 | Available |  | RAD
150 |  | DP-RDR-7310 | DP-RDR-7310-V1-AS-x86_64 |  |  |  | 7 | 2025-05-23 | 2025-06-04 | 12 | Available |  | RAD
151 | YEC2829 | DP-RDR-8134 | DP-RDR-8134-630-UTILITIES |  | Completed | Completed | 7 | 2025-07-30 | 2025-08-26 | 27 | Available |  | RAD
152 |  |  | DP-RDR-8134-630-V1-AS-RC-SIM |  |  |  | 16 | 2025-05-23 | 2025-11-11 | 172 | Available |  | RAD
153 |  |  | DP-RDR-8134-630-V1-AS-RVP-SIM |  |  |  | 13 | 2025-05-23 | 2025-12-18 | 209 | Available |  | RAD
154 |  |  | DP-RDR-8134-630-V1-AS-SP-SIM |  |  |  | 12 | 2025-05-23 | 2025-12-04 | 195 | Available |  | RAD
155 | YIA2647 | DP-RDR-7388 |  |  | Completed | Completed | 0 |  |  | 0 | Not available |  | RAD
156 |  | DP-RDR-8134 |  |  |  |  | 18 | 2025-06-09 | 2025-12-18 | 192 | Available |  | RAD
157 | YEC2693 | DP-RTS-8006 | DP-RTS-8006-600-V1-AS-Arch-OS |  | Completed | Completed | 7 | 2025-01-02 | 2026-02-11 | 405 | Available |  | RAD
158 |  |  | DP-RTS-8006-V1-AS-RTSCA-PPC64-LIN3V8 |  |  |  | 20 | 2025-01-02 | 2026-02-11 | 405 | Available |  | RAD
159 | YEB2694 |  | RTSC |  | Completed | Completed | 0 | 2025-01-25 | 2026-02-11 | 382 | Available |  | RAD
160 | YEB2104 |  | RC |  | Completed | Customer support | 0 |  |  |  | Available |  | RAD
161 |  |  | SP |  |  |  | 0 |  |  |  | Available |  | RAD
162 |  |  | SSU |  |  |  | 0 |  |  |  | Available |  | RAD
163 | YIB2842 | - | - |  | Just Started | Requirement | 0 |  |  | 0 | Not available |  | RAD
164 | YIC2759 | - | - | Arun | Just Started | Requirement | 0 |  |  | 0 | Not available |  | RAD
165 | YIA2822 | DP-CRF-6419 | AS |  |  |  | 0 |  |  | 0 | Not available |  | RAD
166 |  | DP-RDR-7474 | ERP_ATP_TARGET |  | Testing | Testing | 28 | 2025-07-09 | 2026-01-16 | 191 | Available |  | RAD
167 |  |  | ERP_GUI |  | Testing | Testing | 76 | 2025-01-29 | 2026-02-11 | 378 | Available |  | RAD
168 |  | DP-RDR-7477 | AAAU_GUI |  | Implementation | Implementation | 60 | 2025-01-02 | 2026-02-11 | 405 | Available |  | RAD
169 |  | DP-RDR-8245 | CMS |  |  |  | 2 | 2026-02-11 | 2026-02-12 | 1 | Available |  | RAD
170 |  |  | DRSP |  |  |  | 34 | 2025-03-13 | 2025-11-14 | 246 | Available |  | RAD
171 |  |  | OBC_SIM |  |  |  | 4 | 2025-12-24 | 2026-01-29 | 36 | Available |  | RAD
172 |  |  | RSP-A |  |  |  | 26 | 2025-06-02 | 2026-02-12 | 255 | Available |  | RAD
173 |  |  | RSP_Slave |  |  |  | 23 | 2025-07-08 | 2026-02-11 | 218 | Available |  | RAD
174 |  |  | SYS_GUI |  |  |  | 10 | 2025-03-13 | 2025-04-24 | 42 | Available |  | RAD
175 |  |  | SYS_TARGET |  |  |  | 54 | 2025-07-10 | 2026-01-29 | 203 | Available |  | RAD
176 | YEA2707 | DP-RDR-8140 | RCMS |  | Customer Support | Customer Support | 6 | 2024-12-30 | 2025-12-29 | 364 | Available |  | RAD
177 |  |  | RSCA |  |  |  | 6 | 2024-12-30 | 2025-12-02 | 337 | Available |  | RAD
178 |  |  | RSP |  |  |  | 6 | 2025-12-02 | 2025-12-02 | 0 | Available |  | RAD
179 |  |  | PATA-GUI |  | Completed | Completed | 6 | 2025-04-26 | 2025-04-28 | 2 | Available |  | RAD
180 | SIB2999 | DP-SWR-8005 | PARDP-BRIDGE |  | Implementation | Implementation | 19 | 2025-11-28 | 2026-02-11 | 75 | Available |  | RAD
181 |  |  | PARDP-RECORDER |  |  |  | 10 | 2025-09-23 | 2026-02-11 | 141 | Available |  | RAD
182 |  |  | PARDP-TRACKER |  |  |  | 10 | 2025-09-23 | 2026-02-11 | 141 | Available |  | RAD
183 |  |  | PARDD |  |  |  | 19 | 2025-09-23 | 2026-02-11 | 141 | Available |  | RAD
184 |  |  | PARSIM |  |  |  | 12 | 2025-09-23 | 2026-02-11 | 141 | Available |  | RAD
185 |  |  | PARFS |  | Just Started Implementation |  | 8 | 2025-09-23 | 2026-01-06 | 105 | Available |  | RAD
186 | YEA2876 | DP-SPL-6735 | FWS |  | Testing | Testing | 13 | 6 Nov 2025 | 12 Feb 2026 | 98 | Yes |  | AGM
187 |  | IT-SPL-5003 | AS |  |  |  | 4 | 5 Dec 2025 | 10 Feb 2026 | 67 | Yes |  | AGM
188 |  |  | BLS |  |  |  | 3 | 5 Dec 2025 | 22 Dec 2025 | 17 | Yes |  | AGM
189 |  |  | FWS |  |  |  | 4 | 5 Dec 2025 | 20 Jan 2026 | 46 | Yes |  | AGM
190 |  | IT-SPL-5000 | FWS |  |  |  | 2 | 4 Jun 2025 | 12 Jun 2025 | 8 | Yes |  | AGM
191 |  |  | AS |  |  |  | 2 | 4 Jun 2025 | 12 Jun 2025 | 8 | Yes |  | AGM
192 |  | DP-SPL-7306 | FWS |  |  |  | 0 | - | - |  | No |  | AGM
193 |  |  | AS |  |  |  | 0 | - | - |  | No |  | AGM
194 |  | DP-SPL-7123 | FWS |  |  |  | 0 | - | - |  | No |  | AGM
195 |  |  | AS |  |  |  | 0 | - | - |  | No |  | AGM
196 | YIB2815 | DP-SPL-4003 | AS |  |  |  | 4 | 12 Jul 2025 | 17 Jul 2025 | 5 | Yes |  | AGM
197 |  |  | FWS |  |  |  | 7 | 12 Jul 2025 | 20 Jan 2026 | 192 | Yes |  | AGM
198 |  | DP-PSU-7357 | AS |  |  |  | 1 | 22 Dec 2025 | 22 Dec 2025 | 0 | Yes |  | AGM
199 |  |  | FWS |  |  |  | 1 | 22 Dec 2025 | 22 Dec 2025 | 0 | Yes |  | AGM
200 |  | DP-PSU-8287 | AS |  |  |  | 0 | - | - |  | No |  | AGM
201 |  |  | FWS |  |  |  | 0 | - | - |  | No |  | AGM
202 | YEB2986 | DP-SPL-5452 | AS |  | Testing | Testing | 3 | 1 Jan 2026 | 12 Feb 2026 | 42 | Yes |  | AGM
203 |  |  | FWS |  |  |  | 4 | 1 Jan 2026 | 12 Feb 2026 | 42 | Yes |  | AGM
204 |  | DP-VPX-3611 | AS |  | Dropped | Dropped | 1 | 9 Dec 2025 | 9 Dec 2025 | 0 | Yes |  | AGM
205 |  |  | FWS |  |  |  | 1 | 9 Dec 2025 | 9 Dec 2025 | 0 | Yes |  | AGM
206 | YEB2929 | DP-RDR-8314 | WPR AS |  | Testing | Testing | 60 | 25 Feb 2025 | 6 Aug 2025 | 162 | Yes |  | AGM
207 |  | DP-SPL-7183 | TRM AS |  | Hold | Hold | 2 | 4 Jun 2025 | 13 Jun 2025 | 9 | Yes |  | AGM
208 | YEC2708 | DP-COM-8031-630 | L-Band FWS |  | Implementation | Implementation | 5 | 13 Jun 2025 | 20 Jan 2026 | 221 | Yes |  | AGM
209 |  |  | UHF FWS |  |  |  | 6 | 13 Jun 2025 | 20 Jan 2026 | 221 | Yes |  | AGM
210 |  | DP-COM-8031-633 | L-Band FWS |  |  |  | 3 | 13 Jun 2025 | 22 Sep 2025 | 101 | Yes |  | AGM
211 |  |  | UHF FWS |  |  |  | 1 | 13 Jun 2025 | 13 Jun 2025 | 0 | No |  | AGM
212 | YIC2835 | DP-TRM-8030 | AS |  |  |  | 1 | 9 Dec 2025 | 9 Dec 2025 | 0 | No |  | AGM
213 |  |  | FWS |  |  |  | 1 | 9 Dec 2025 | 9 Dec 2025 | 0 | No |  | AGM
214 | YIB2842 |  |  |  | Requirements | Requirements | 0 | - | - |  | No |  | AGM
215 | YEA2846 | DP-ROM-8036 | AS |  | Testing | Testing | 2 | 1 Jan 2026 | 12 Feb 2026 | 42 | Yes |  | AGM
217 | YEC2826 | DP-CRF-7556 PLL | AS |  | Testing | Testing | 2 | 1 Oct 2025 | 10 Feb 2026 | 132 | Yes |  | AGM
218 |  |  | FWS |  |  |  | 2 | 1 Oct 2025 | 10 Feb 2026 | 132 | Yes |  | AGM
219 | YEA2930 | DP-CRF-2213 | AS |  | Completed | Completed | 7 | 10 Dec 2025 | 20 Jan 2026 | 41 | Yes |  | AGM
220 |  |  | FWS |  |  |  | 2 | 10 Dec 2025 | 22 Dec 2025 | 12 | Yes |  | AGM
221 |  | DP-CRF-2519 | AS |  |  |  | 2 | 9 Dec 2025 | 15 Dec 2025 | 6 | Yes |  | AGM
222 |  |  | FWS |  |  |  | 2 | 9 Dec 2025 | 15 Dec 2025 | 6 | Yes |  | AGM
223 |  | DP-CRF-5366 | AS |  |  |  | 5 | 10 Dec 2025 | 20 Jan 2026 | 41 | Yes |  | AGM
224 |  |  | FWS |  |  |  | 5 | 10 Dec 2025 | 20 Jan 2026 | 41 | Yes |  | AGM
225 |  | DP-CRF-5369 | AS |  |  |  | 2 | 10 Dec 2025 | 15 Dec 2025 | 5 | Yes |  | AGM
226 |  |  | FWS |  |  |  | 2 | 10 Dec 2025 | 15 Dec 2025 | 5 | Yes |  | AGM
227 | YEA2612 | DP-EW-8002-699 | AS |  | Completed | Completed | 6 | 20 Nov 2025 | 10 Oct 2025 | -41 | Yes |  | AGM
228 |  |  | FWS |  |  |  | 7 | 15 Nov 2025 | 8 Oct 2025 | -38 | Yes |  | AGM
229 | YEB2787 | DP-EW-8002-630 | AS |  | Completed | Completed | 4 | 2 Aug 2025 | 3 Sep 2025 | 32 | Yes |  | AGM
230 |  |  | FWS |  |  |  | 6 | 2 Aug 2025 | 3 Sep 2025 | 32 | Yes |  | AGM
231 | YIA2891 | - | - |  | Old Project | Old Project | 0 | - | - |  | - |  | AGM
232 | YEC2793 | - | - |  | Old Project | Old Project | 0 | - | - |  | - |  | AGM
233 | YIC2871 | - | - |  | Requirements | Requirements | 0 | - | - |  | - |  | AGM
234 | YEB3031 | - | - |  | Requirements | Requirements | 0 | - | - |  | - |  | AGM
235 | YIC2814 | - | - |  | Old Project | Old Project | 0 | - | - |  | - |  | AGM
236 | YEB3103 | - | - |  | Not Started | Not Started | 0 | - | - |  | - |  | AGM
237 | YIC2665 | DP-ESM-1095-600-AIDF | AS |  | Completed | Completed | 1 | 5 Dec 2025 | 5 Dec 2025 | 0 | Yes |  | AGM
238 |  |  | FWS |  |  |  | 1 | 5 Dec 2025 | 5 Dec 2025 | 0 | Yes |  | AGM
239 |  | DP-ESM-1095-603-MIDF | AS |  |  |  | 1 | 5 Dec 2025 | 5 Dec 2025 | 0 | Yes |  | AGM
240 |  |  | FWS |  |  |  | 1 | 5 Dec 2025 | 5 Dec 2025 | 0 | Yes |  | AGM
241 |  | DP-ESM-1098-600-CFDF | AS |  |  |  | 1 | 5 Dec 2025 | 8 Dec 2025 | 3 | Yes |  | AGM
242 |  |  | FWS |  |  |  | 1 | 5 Dec 2025 | 8 Dec 2025 | 3 | Yes |  | AGM
243 |  | DP-ESM-1098-603-MRA | AS |  |  |  | 1 | 5 Dec 2025 | 8 Dec 2025 | 3 | Yes |  | AGM
244 |  |  | FWS |  |  |  | 1 | 5 Dec 2025 | 8 Dec 2025 | 3 | Yes |  | AGM
245 | YEB2935 | DP-ESM-1212-6033-VUSHF-Mrx | AS |  | Implementation | Implementation | 15 | 24 Jul 2025 | 4 Feb 2026 | 195 | Yes |  | AGM
246 |  |  | DS |  |  |  | 1 | 13 Aug 2025 | 13 Aug 2025 | 0 | Yes |  | AGM
247 |  |  | FWS |  |  |  | 15 | 9 Aug 2025 | 9 Feb 2026 | 184 | Yes |  | AGM
248 |  | DP-ESM-1074-6000-VUSHF-RPE | AS |  | Testing | Testing | 7 | 13 Aug 2025 | 14 Feb 2026 | 185 | Yes |  | AGM
249 |  |  | FWS |  |  |  | 8 | 13 Aug 2025 | 14 Feb 2026 | 185 | Yes |  | AGM
250 |  |  | DS |  |  |  | 3 | 13 Aug 2025 | 31 Jan 2026 | 171 | Yes |  | AGM
251 |  |  | AS |  | Implementation | Implementation | 1 | 2 Feb 2026 | 2 Feb 2026 | 0 | Yes |  | AGM
252 |  |  | FWS |  |  |  | 1 | 2 Feb 2026 | 2 Feb 2026 | 0 | Yes |  | AGM
253 |  |  | DS |  |  |  | 1 | 2 Feb 2026 | 2 Feb 2026 | 0 | Yes |  | AGM
254 |  | DP-ESM-1073-6333-HF-RPE | AS |  | Testing | Testing | 15 | 20 Aug 2025 | 4 Feb 2026 | 168 | Yes |  | AGM
255 |  |  | DS |  |  |  | 3 | 8 Aug 2025 | 23 Jan 2026 | 168 | Yes |  | AGM
256 |  |  | FWS1 |  |  |  | 9 | 8 Aug 2025 | 30 Jan 2026 | 175 | Yes |  | AGM
257 |  |  | FWS2 |  |  |  | 11 | 8 Aug 2025 | 4 Feb 2026 | 180 | Yes |  | AGM
258 | YEC2865 | DP-OBC-1149 | DP-OBC-1149-V1-01-AS-x86-WIN | Madhusudhan Dangeti | Completed | Completed | 34 | 10 Jun 2024 | 9 Jan 2026 | 578 | Yes |  | Application
259 |  | DP-OBC-5028 | DP-OBC-5028-V1-01-AS-x86-WIN |  |  |  | 44 | 10 Jun 2024 | 9 Jan 2026 | 578 | Yes |  | Application
260 |  | DP-OBC-3012 | DP-OBC-3012-V1-01-AS-x86-WIN |  |  |  | 12 | 7 Nov 2024 | 9 Jan 2026 | 428 | Yes |  | Application
261 |  |  | DP-OBC-3012-V1-01-FWS-ATSAMRH71F20C |  |  |  | 13 | 7 Nov 2024 | 29 Nov 2025 | 387 | Yes |  | Application
262 | YEA2776 | DP-COMM-8037 | DP-COMM-8037-02-V1-AS-X86-W7 | Mahesh K V | Completed | Completed | 12 | 31 Oct 2025 | 30 Dec 2025 | 60 | Yes |  | Application
263 |  |  | DP-COMM-8037-02-V1-FWS-ARM-LINUX |  |  |  | 10 | 31 Oct 2025 | 30 Dec 2025 | 60 | Yes |  | Application
264 |  | DP-CRF-5325 | DP-CRF-5325-V1-AS-X86-WIN |  |  |  | 24 | 4 Jun 2025 | 6 Jan 2026 | 216 | Yes |  | Application
265 |  |  | DP-CRF-5325-V1-FWS-ATSAMD51G19A |  |  |  | 16 | 29 Jan 2025 | 24 Dec 2025 | 329 | Yes |  | Application
266 | YEB2989 | DP-ECM-1074 | DP-ECM-1074-660-V1-AS-X86-WIN | Arun Kumar B | Requirement | Requirement | 1 | 11 Feb 2026 | 11 Feb 2026 | 0 | Yes |  | Application
267 |  |  | DP-ECM-1074-660-V1-DS-ARM64-LIN |  |  |  | 1 | 11 Feb 2026 | 11 Feb 2026 | 0 | Yes |  | Application
268 |  |  | DP-ECM-1074-660-V1-FWS-ARM64-LIN |  |  |  | 1 | 11 Feb 2026 | 11 Feb 2026 | 0 | Yes |  | Application
269 | YEA2588 | DP-EW-8014 | DP-EW-8014-660-V1-01-AS-X86-W7 | Venkatasalapathi K | Completed | Completed | 1 | 5 Dec 2025 | 5 Dec 2025 | 0 | Yes |  | Application
270 |  |  | DP-EW-8014-660-V1-01-FWS-PPC-LX |  |  |  | 1 | 5 Dec 2025 | 5 Dec 2025 | 0 | Yes |  | Application
271 | YEA2255 |  | YEA2255_UAV_AS | Arun Kumar B | Completed | Completed | 27 | 14 May 2025 | 2 Feb 2026 | 264 | Yes |  | Application
272 |  |  | YEA2255_UAV_FWS |  |  |  | 22 | 14 May 2025 | 2 Feb 2026 | 264 | Yes |  | Application
273 | YEA2255 |  | DP_IELINT_AEWC_AS | Arun Kumar B | Completed | Completed | 14 | 21 Nov 2025 | 2 Feb 2026 | 73 | Yes |  | Application
274 |  |  | DP_IELINT_AEWC_FWS |  |  |  | 11 | 21 Nov 2025 | 13 Feb 2026 | 84 | Yes |  | Application
275 | YIA2652 | DP-ESM-1062 | DP-ESM-1062-V1-AS-9ELEMENT_5CH_IntraPulseAnalyzer-x86-WIN |  |  |  | 0 | - | - |  | No |  | Application
276 |  |  | DP-ESM-1062-V1-AS-9ELEMENT_5CH_Standalone-x86-WIN | Venkatasalapathi K | Testing | Testing | 10 | 23 Jan 2026 | 2 Feb 2026 | 10 | Yes |  | Application
277 |  |  | DP-ESM-1062-V1-AS-CONTROLCENTER-x86-WIN |  |  |  | 9 | 23 Jan 2026 | 24 Jan 2026 | 1 | Yes |  | Application
278 |  |  | DP-ESM-1062-V1-DS-9ELEMENT_5CH-ARM64-LINUX |  |  |  | 7 | 23 Jan 2026 | 24 Jan 2026 | 1 | Yes |  | Application
279 |  |  | DP-ESM-1062-V1-FWS-9ELEMENT_5CH_MRx-ARM64-LINUX |  |  |  | 3 | 23 Jan 2026 | 24 Jan 2026 | 1 | Yes |  | Application
280 |  |  | DP-ESM-1062-V1-FWS-9ELEMENT_5CH_SRx-ARM64-LINUX |  |  |  | 9 | 23 Jan 2026 | 2 Feb 2026 | 10 | Yes |  | Application
281 |  | DP-CRF-6308 | DP-CRF-6308-V1-AS-x86-WIN |  |  |  | 1 | 4 Feb 2026 | 4 Feb 2026 | 0 | Yes |  | Application
282 |  | DP-CRF-6398 | DP-CRF-6398-V1-AS-x86-WIN |  |  |  | 3 | 24 Jan 2026 | 4 Feb 2026 | 11 | Yes |  | Application
283 | YEC2750 |  | YEC2750_APP | Naveen C | Completed | Completed | 41 | 2 Jan 2025 | 31 Dec 2025 | 363 | Yes |  | Application
284 |  |  | YEC2750_DS_0930 |  |  |  | 1 | 7 Jan 2025 | 7 Jan 2025 | 0 | Yes |  | Application
285 |  |  | YEC2750_DS_5028 |  |  |  | 1 | 7 Jan 2025 | 7 Jan 2025 | 0 | Yes |  | Application
286 |  |  | YEC2750_FWS |  |  |  | 39 | 7 Jan 2025 | 26 Jan 2025 | 19 | Yes |  | Application
287 |  |  | YEC2750_IPA |  |  |  | 5 | 7 Jan 2025 | 19 Jun 2025 | 163 | Yes |  | Application
288 | YEC2934 |  | YEC2934_BEL_NBRFLRU_2BLI_AS | Naveen C | DEMO | DEMO | 1 | 10 Jan 2025 | 12 Jan 2025 | 2 | Yes |  | Application
289 |  |  | YEC2934_BEL_NBRFLRU_2BLI_FWS |  |  |  | 1 | 10 Jan 2025 | 12 Jan 2025 | 2 | Yes |  | Application
290 |  | DP-CRF-7553 | DP-CRF-7553-V1-AS-X86-WIN |  |  |  | 7 | 10 Jan 2025 | 22 Sep 2025 | 255 | Yes |  | Application
291 |  |  | DP-CRF-7553-V1-FWS-XMEGA |  |  |  | 7 | 10 Jan 2025 | 22 Sep 2025 | 255 | Yes |  | Application
292 | YIB2815 | DP-ECM-1215 | DP-ECM-1215-603-V1-AS-X86-W10 | Linto Thomas | Implementation | Implementation | 40 | 3 Dec 2024 | 13 Feb 2026 | 437 | Yes |  | Application
293 |  |  | DP-ECM-1215-603-V1-FWS-ARM64-LINUX |  |  |  | 45 | 3 Dec 2024 | 12 Feb 2026 | 436 | Yes |  | Application
294 | YIA2813 | DP-EW-8002 | DP-EW-8002-663-V1-AS-X86-WIN-1V00 | Vadivel A | Completed | Completed | 4 | 31 Jul 2025 | 22 Dec 2025 | 144 | Yes |  | Application
295 |  |  | DP-EW-8002-663-V1-FWS-PPC-LX-1V00 |  |  |  | 2 | 31 Jul 2025 | 22 Dec 2025 | 144 | Yes |  | Application
296 | YIB2821 | DP-SPL-6907 | DP-SPL-6907-V1-AS-X86-WIN10 | Mahesh K V | Completed | Completed | 1 | 10 Nov 2025 | 25 Nov 2025 | 15 | Yes |  | Application
297 |  |  | DP-SPL-6907-V1-FWS-ATXMEGA128A4U |  |  |  | 1 | 10 Nov 2025 | 25 Nov 2025 | 15 | Yes |  | Application
298 | YEA2936 | DP-DMCS-8125 | DP-DMCS-8125-V1-02-AS-x86-WIN | Madhusudhan Dangeti | Testing | Testing | 0 | - | - |  | No |  | Application
299 |  |  | DP-DMCS-8125-V1-02-FWS-ADSP21569 |  |  |  | 0 | - | - |  | No |  | Application
300 | YEB3076 | - | - | Venkatasalapathi K | Requirement | Requirement | 0 | - | - |  | No |  | Application
301 | YEC2877 | DP-CRF-7463 | - | Mahesh K V | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
302 | YEA2939 | DP-ATE-8210 | - | Mahesh K V | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
303 | YEC2952 | DP-ATE-8210 | - | Mahesh K V | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
304 | YEC2691 | - | - | Madhusudhan Dangeti | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
305 | YIC2820 | - | - | Madhusudhan Dangeti | Requirement | Requirement | 0 |  |  | 0 | No |  | Application
306 | YIB2784 | - | - |  | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
307 | YIA2819 | - | - |  | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
308 | YEB2143 | - | - |  | Completed before Apr 2025 | Completed before Apr 2025 | 0 | - | - |  | No |  | Application
309 | YEB2775 | - | - |  | Requirement | Requirement | 0 | - | - |  | No |  | Application
310 | YEA2918 | DP-OBC-8178 | DP-OBC-8178-V1-02-LIB-LINUX-OS | Madhusudhan Dangeti | Completed | Completed | 35 | 2025-06-04 | 2026-01-09 | 219 | Yes |  | Application
311 |  | DP-OBC-8178-V1-02-US-LINUX | DP-OBC-8178-V1-02-US-LINUX |  |  |  | 12 | 2025-06-12 | 2025-10-29 | 139 | Yes |  | Application
312 | YIA2822 | DP-TMC-8148 | - |  | Completed | Completed | 0 |  |  |  | No |  | Application
313 | YEB2694 | DP-RDR-8167 | DP-RDR-8167-V1-01-AS-HOST-X86_64-W10 | Poovarasan S | Completed | Completed | 31 | 2025-03-06 | 2025-09-19 | 197 | Yes |  | Application
314 |  |  | DP-RDR-8167-V1-01-LIBS-HOST-X86_64-W10 |  | Completed | Completed | 6 | 2025-03-06 | 2025-04-07 | 32 | Yes |  | Application
315 |  |  | DP-RDR-8167-V1-01-AS-TARGET-AARCH64-LIN5V10 |  | Completed | Completed | 7 | 2025-03-06 | 2025-08-14 | 161 | Yes |  | Application
316 |  |  | DP-RDR-8167-V1-02-AS-HOST-X86_64-W10 |  | Completed | Completed | 3 | 2025-03-06 | 2025-03-10 | 4 | Yes |  | Application
317 |  |  | DP-RDR-8167-V1-02-LIBS-X86_64-W10 |  | Completed | Completed | 3 | 2025-03-06 | 2025-03-10 | 4 | Yes |  | Application
318 |  |  | DP-ATE-8420-V1-01-AS-RSU-HOST-x86_64-W10 |  | On-Going | On-Going | 74 | 2025-03-08 | 2025-12-11 | 278 | Yes |  | Application
319 |  |  | DP-ATE-8420-V1-01-AS-RSU-OPU-AARCH64-LIN5V10 |  | On-Going | On-Going | 10 | 2025-03-08 | 2025-12-10 | 277 | Yes |  | Application
320 |  | DP-RDR-8164 | DP-RDR-8164-V1-01-AS-HOST-X86_64-W10 | Poovarasan S | Completed | Completed | 49 | 2025-03-06 | 2025-10-31 | 239 | Yes |  | Application
321 |  |  | DP-RDR-8164-V1-01-AS-IFM-DPSPL0220-660-AARCH64-LIN5V10 |  | Completed | Completed | 2 | 2025-03-12 | 2025-04-08 | 27 | Yes |  | Application
322 |  |  | DP-RDR-8164-V1-01-AS-TARGET-AARCH64-LIN5V10 |  | Completed | Completed | 9 | 2025-03-06 | 2025-08-09 | 156 | Yes |  | Application
323 |  |  | DP-RDR-8164-V1-02-AS-HOST-X86_64-W10 |  | Completed | Completed | 6 | 2025-03-06 | 2025-07-08 | 124 | Yes |  | Application
324 |  |  | DP-RDR-8164-V1-02-LIBS-HOST-X86_64-W10 |  | Completed | Completed | 7 | 2025-03-06 | 2025-07-08 | 124 | Yes |  | Application
325 |  |  | DP-ATE-8420-V1-01-AS-SCPU-HOST-x86_64-W10 |  | On-Going | On-Going | 8 | 2025-03-08 | 2025-12-01 | 268 | Yes |  | Application
326 |  |  | DP-ATE-8420-V1-01-AS-SCPU-OPU-AARCH64-LIN5V10 |  | On-Going | On-Going | 29 | 2025-03-08 | 2025-12-11 | 278 | Yes |  | Application
327 |  | DP-RDR-8170 | DP-RDR-8170-V1-01-AS-HOST-X86_64-W10 | Poovarasan S | Completed | Completed | 33 | 2025-03-06 | 2025-09-22 | 200 | Yes |  | Application
328 |  |  | DP-RDR-8170-V1-01-AS-IFM-DPSPL0220-660-AARCH64-LIN5V10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
329 |  |  | DP-RDR-8170-V1-01-AS-TARGET-AARCH64-LIN5V10 |  | Completed | Completed | 10 | 2025-03-06 | 2025-08-09 | 156 | Yes |  | Application
330 |  |  | DP-RDR-8170-V1-02-LIBS-X86_64-W10 |  | Completed | Completed | 4 | 2025-03-06 | 2025-03-20 | 14 | Yes |  | Application
331 |  |  | DP-RDR-8170-V1-02-AS-HOST-X86_64-W10 |  | Completed | Completed | 4 | 2025-03-06 | 2025-03-20 | 14 | Yes |  | Application
332 |  |  | DP-ATE-8420-V1-01-AS-FDBF-HOST-x86_64-W10 |  | On-Going | On-Going | 20 | 2025-03-08 | 2025-12-11 | 278 | Yes |  | Application
333 |  |  | DP-ATE-8420-V1-01-AS-FDBF-OPU-AARCH64-LIN5V10 |  | On-Going | On-Going | 6 | 2025-03-08 | 2025-12-10 | 277 | Yes |  | Application
334 |  | DP-SPU-8019 | DP-SPU-8019-V1-01-AS-HOST-X86_64-W10 | Rajesh P | Completed | Completed | 3 | 2025-03-10 | 2025-09-02 | 176 | Yes |  | Application
335 |  |  | DP-SPU-8019-V1-01-AS-TARGET-DPVPX0753-RHEL9V2 |  | Completed | Completed | 5 | 2025-01-24 | 2025-05-20 | 116 | Yes |  | Application
336 |  |  | DP-ATE-8420-V1-01-AS-SPU-HOST-x86_64-W10 |  | On-Going | On-Going | 1 | 2025-06-30 | 2025-06-30 | 0 | Yes |  | Application
337 |  |  | DP-ATE-8420-V1-01-AS-SPU-TARGET-DPVPX0753-RHEL9V2 |  | On-Going | On-Going | 1 | 2025-06-30 | 2025-06-30 | 0 | Yes |  | Application
338 |  |  | DP-ATE-8420-V1-01-AS-SPU-OPU-AARCH64-LIN5V10 |  | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
339 |  | DP-DTRM-8019 | DP-DTRM-8019-V1-01-AS-HOST-X86_64-W10 | Yashenth A M | Completed | Completed | 4 | 2025-01-24 | 2025-08-07 | 195 | Yes |  | Application
340 |  |  | DP-DTRM-8019-V1-01-AS-IFM-DPSPL0220-660-AARCH64-LIN5V10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
341 |  |  | DP-DTRM-8019-V1-02-AS-HOST-X86_64-W10 |  | Completed | Completed | 2 | 2025-01-24 | 2025-01-24 | 0 | Yes |  | Application
342 |  |  | DP-DTRM-8019-V1-02-LIBS-X86_64-W10 |  | Completed | Completed | 3 | 2025-01-24 | 2025-01-29 | 5 | Yes |  | Application
343 |  |  | DP-ATE-8420-V1-01-AS-ODTRM-HOST-x86_64-W10 |  | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
344 |  |  | DP-ATE-8420-V1-01-AS-ODTRM-OPU-AARCH64-LIN5V10 |  | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
345 |  | DP-DRM-8011 | DP-DRM-8011-V1-01-AS-HOST-X86_64-W10 | Yashenth A M | Completed | Completed | 10 | 2025-02-11 | 2025-08-18 | 188 | Yes |  | Application
346 |  |  | DP-DRM-8011-V1-02-AS-HOST-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
347 |  |  | DP-DRM-8011-V1-02-LIBS-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
348 |  |  | DP-ATE-8420-V1-01-AS-ODRM-HOST-x86_64-W10 |  | On-Going | On-Going | 9 | 2025-02-11 | 2025-06-05 | 114 | Yes |  | Application
349 |  | DP-ATE-8420 | DP-ATE-8420-V1-01-AS-ST-HOST-x64-W10 | Rajesh P | On-Going | On-Going | 15 | 2025-06-03 | 2026-01-05 | 216 | Yes |  | Application
350 | YEC2693 | DP-RDR-8161 | DP-RDR-8161-V1-01-AS-HOST-X86_64-W10 | Sridhar J | Completed | Completed | 3 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
351 |  |  | DP-RDR-8161-V1-01-AS-TARGET-AARCH64-LIN5V10 |  | Completed | Completed | 2 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
352 |  | DP-RDR-8176 | DP-RDR-8176-V1-01-LIBS-X86_64-W10 | Sridhar J | Completed | Completed | 2 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
353 |  |  | DP-RDR-8176-V1-01-AS-X86_64-W10 |  | Completed | Completed | 2 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
354 |  |  | DP-RDR-8176-V1-02-AS-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
355 |  |  | DP-ATE-8423-V1-01-LIBS-CMM-X86_64-W10 |  | On-Going | On-Going | 2 | 2025-06-05 | 2025-06-06 | 1 | Yes |  | Application
356 |  |  | DP-ATE-8423-V1-01-AS-CMM-X86_64-W10 |  | On-Going | On-Going | 5 | 2025-06-05 | 2025-08-25 | 81 | Yes |  | Application
357 |  |  | DP-ATE-8423-V1-01-AS-OPU-AARCH64-LIN5V10 |  | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
358 |  | DP-RDR-8179 | DP-RDR-8179-V1-01-LIBS-X86_64-W10 | Rajendrakumar S | Completed | Completed | 3 | 2025-05-22 | 2025-05-28 | 6 | Yes |  | Application
359 |  |  | DP-RDR-8179-V1-01-AS-X86_64-W10 |  | Completed | Completed | 2 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
360 |  |  | DP-RDR-8179-V1-02-AS-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
361 |  |  | DP-ATE-8423-V1-01-LIBS-CCMU-X86_64-W10 |  | On-Going | On-Going | 9 | 2025-01-28 | 2025-05-28 | 120 | Yes |  | Application
362 |  |  | DP-ATE-8423-V1-01-AS-CCMU-X86_64-W10 |  | On-Going | On-Going | 2 | 2025-01-28 | 2025-05-28 | 120 | Yes |  | Application
363 |  | DP-RDR-8182 | DP-RDR-8182-V1-01-LIBS-X86_64-W10 | Rajendrakumar S | Completed | Completed | 3 | 2025-06-05 | 2025-06-06 | 1 | Yes |  | Application
364 |  |  | DP-RDR-8182-V1-01-AS-X86_64-W10 |  | Completed | Completed | 4 | 2025-06-05 | 2025-06-11 | 6 | Yes |  | Application
365 |  |  | DP-RDR-8182-V1-02-AS-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
366 |  |  | DP-ATE-8423-V1-01-LIBS-SPU-X86_64-W10 |  | On-Going | On-Going | 5 | 2025-06-05 | 2025-08-25 | 81 | Yes |  | Application
367 |  |  | DP-ATE-8423-V1-01-AS-SPU-X86_64-W10 |  | On-Going | On-Going | 6 | 2025-06-05 | 2025-08-25 | 81 | Yes |  | Application
368 |  | DP-RDR-8185 | DP-RDR-8185-V1-01-LIBS-X86_64-W10 | Rajendrakumar S | Completed | Completed | 4 | 2025-06-05 | 2025-06-06 | 1 | Yes |  | Application
369 |  |  | DP-RDR-8185-V1-01-AS-X86_64-W10 |  | Completed | Completed | 6 | 2025-06-05 | 2025-06-11 | 6 | Yes |  | Application
370 |  |  | DP-RDR-8185-V1-02-AS-X86_64-W10 |  |  |  | 0 |  |  | 0 | No |  | Application
371 |  |  | DP-ATE-8423-V1-01-LIBS-CSPU-X86_64-W10 |  | On-Going | On-Going | 2 | 2025-06-05 | 2025-06-06 | 1 | Yes |  | Application
372 |  |  | DP-ATE-8423-V1-01-AS-CSPU-X86_64-W10 |  | On-Going | On-Going | 5 | 2025-06-05 | 2025-08-25 | 81 | Yes |  | Application
373 |  | DP-RDR-8188 | DP-RDR-8188-V1-01-LIBS-X86_64-W10 | Sridhar J | Completed | Completed | 3 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
374 |  |  | DP-RDR-8188-V1-01-AS-X86_64-W10 |  | Completed | Completed | 3 | 2025-05-22 | 2025-05-22 | 0 | Yes |  | Application
375 |  |  | DP-RDR-8188-V1-02-AS-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
376 |  |  | DP-ATE-8423-V1-01-LIBS-STPU-X86_64-W10 |  | On-Going | On-Going | 5 | 2025-06-05 | 2025-08-25 | 81 | Yes |  | Application
377 |  |  | DP-ATE-8423-V1-01-AS-STPU-X86_64-W10 |  | On-Going | On-Going | 6 | 2025-06-05 | 2025-08-25 | 81 | Yes |  | Application
378 |  | DP-DTM-8003 | DP-DTM-8003-V1-01-LIBS-X86_64-W10 | Kishore N |  |  | 0 |  |  | 0 | No |  | Application
379 |  |  | DP-DTM-8003-V1-01-AS-X86_64-W10 |  | Completed | Completed | 9 | 2025-03-20 | 2025-06-19 | 91 | Yes |  | Application
380 |  |  | DP-DTM-8003-V1-02-AS-X86_64-W10 |  | Completed | Completed | 0 |  |  | 0 | No |  | Application
381 |  |  | DP-ATE-8423-V1-01-AS-DTM-X86_64-W10 |  | On-Going | On-Going | 11 | 2025-03-20 | 2025-06-12 | 84 | Yes |  | Application
382 |  | DP-DRM-8008 | DP-DTM-8003-V1-01-LIBS-X86_64-W10 |  |  |  | 0 |  |  | 0 | No |  | Application
383 |  |  | DP-DTM-8003-V1-01-AS-X86_64-W10 |  | Completed | Completed | 9 | 2025-03-20 | 2025-06-19 | 91 | Yes |  | Application
384 |  |  | DP-DTM-8003-V1-02-AS-X86_64-W10 |  |  |  | 0 |  |  | 0 | No |  | Application
385 |  |  | DP-ATE-8423-V1-01-AS-DRM-X86_64-W10 |  | On-Going | On-Going | 9 | 2025-02-10 | 2025-03-25 | 43 | Yes |  | Application
386 |  | DP-RDR-8191 | DP-RDR-8191-V1-01-LIBS-X86_64-W10 | Sridhar J | On-Going | On-Going | 8 | 2025-06-10 | 2025-08-11 | 62 | Yes |  | Application
387 |  |  | DP-RDR-8191-V1-01-AS-X86_64-W10 |  | On-Going | On-Going | 64 | 2025-06-10 | 2025-09-22 | 104 | Yes |  | Application
388 |  |  | DP-RDR-8191-V1-01-AS-TARGET-AARCH64-LIN5V10 |  | On-Going | On-Going | 9 | 2025-06-10 | 2025-07-16 | 36 | Yes |  | Application
389 |  |  | DP-RDR-8191-V1-01-AS-SRV_APP-X64-W10 |  | On-Going | On-Going | 7 | 2025-08-14 | 2025-08-22 | 8 | Yes |  | Application
390 |  | DP-ATE-8423 | DP-ATE-8423-V1-01-AS-ST-HOST-x64-W10 | Rajesh P |  |  | 18 | 2025-06-03 | 2026-01-05 | 216 | Yes |  | Application
391 | YIC2759 | DP-CRF-5273 | DP-CRF-5273-V1-01-AS-X64-W10 | Yashenth A M | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
392 | YIA2822_MIG29K | DP-CRF-6419 | DP-CRF-6419-V1-01-AS-x86_64-W11 | Prasanth S | Completed | Completed | 1 | 2025-09-29 | 2025-09-29 | 0 | Yes |  | Application
393 | YEC2936_ALH | DP-SPL-7180 | DP-SPL-7180-V1-01-AS-x86_64-W11 | Prasanth S | Completed | Completed | 2 | 2025-09-29 | 2025-10-23 | 24 | Yes |  | Application
394 | YIA2927_UHM | DP-CRF-7544 | DP-CRF-7544-V1-01-AS-x86_64-W11 | Prasanth S | On-Going | On-Going | 2 | 2025-09-29 | 2025-10-29 | 30 | Yes |  | Application
395 | YEA2864_AFADECU_ATE | DP-ATE-8456 | DP-ATE-8456-V1-01-AS-SERVER-X86_64-LIN5V14 | Aravinth R | On-Going | On-Going | 35 | 2025-03-12 | 2026-01-10 | 304 | Yes |  | Application
396 | YEA2864_AFADECU_ATE | DP-ATE-8456 | DP-ATE-8456-V1-01-AS-CLIENT-X86_64-LIN5V14 | Aravinth R | On-Going | On-Going | 23 | 2025-03-12 | 2026-01-10 | 304 | Yes |  | Application
397 | YEB3016_600CH_DAS | DP-ATE-8483 | DP-ATE-8483-V1-01-AS-SLV-x86_64-LIN5V14 | Duraisankar V | On-Going | On-Going | 2 | 2025-10-01 | 2025-10-01 | 0 | Yes |  | Application
398 | YEB3016_600CH_DAS | DP-ATE-8483 | DP-ATE-8483-V1-01-AS-MST-x86_64-W11 | Duraisankar V | On-Going | On-Going | 2 | 2025-10-01 | 2025-10-01 | 0 | Yes |  | Application
399 | YEB3016_600CH_DAS | DP-ATE-8483 | DP-ATE-8435-V1-01-AS-OA-X86_64-W11 | Vijaykumar B | On-Going | On-Going | 1 | 2025-10-01 | 2025-10-01 | 0 | Yes |  | Application
400 | YEB3016_600CH_DAS | DP-ATE-8489 | DP-ATE-8489-V1-01-AS-AVD-x86_64-W11 | Duraisankar V | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
401 | YEC2982_CBAND_TRANSMITTER | DP-RDR-8335 | DP-RDR-8335-V1-01-AS-SYS-X86-XEN2V6 | Giriprakash K | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
402 | YEC2982_CBAND_TRANSMITTER | DP-RDR-8335 | DP-RDR-8335-V1-01-AS-RMT-X86-XEN2V6 | Giriprakash K | On-Going | On-Going | 0 |  |  | 0 | No |  | Application
403 | YEB2800 | DP-RFSS-7148 | DP-RFSS-7148-V1-AS-W10 | Abisheck | On-Hold | On-Hold | 12 | 2025-02-05 | 2025-11-11 | 279 | Yes |  | Application
404 |  |  | DP-RFSS-7148-V1-LIBS-W10 |  | On-Hold | On-Hold | 6 | 2025-02-05 | 2025-11-11 | 279 | Yes |  | Application
405 |  | DP-CRF-7457-663 | DP-CRF-7457-663-V1-AS-W10 | Dinesh | On-Going | On-Going | 8 | 2025-12-17 | 2026-02-03 | 48 | Yes |  | Application
406 |  | DP-SPL-7153 | DP-SPL-7153 | Venkatesh/Ramesh | On-Hold | On-Hold | 22 | 2025-02-13 | 2026-02-11 | 363 | Yes |  | Application
407 |  | DP-RFSS-7142 | DP-RFSS-7142 | Venkatesh | Completed | Completed | 107 | 2025-03-05 | 2026-02-02 | 334 | Yes |  | Application
408 |  | DP-ANT-7094 |  |  | Completed | Completed | 0 |  |  | 0 | Yes |  | Application
409 |  | DP-RFSS-7145 | DP-CRF-7145-V1-AS-W10 | Bhavani | On-Going | On-Going | 101 | 2025-02-13 | 2026-02-09 | 361 | Yes |  | Application
410 |  | DP-CRF-7316 | DP-CRF-7316-V1-AS-W10 | Poornima/Venkatesh | Completed | Completed | 102 | 2025-02-05 | 2026-02-11 | 371 | Yes |  | Application
411 |  | DP-CRF-7457 |  |  |  |  | 0 |  |  | 0 | Yes |  | Application
412 | YEC3048 | DP-CRF-5381 | DP-CRF-5381-V1-WIN-AS | Abisheck | On-Going | On-Going | 10 | 2026-02-05 | 2026-02-11 | 6 | Yes |  | Application
413 |  |  | DP-CRF-5381-V1-WIN-LIBS |  | On-Going | On-Going | 1 | 2026-02-05 | 2026-02-05 | 0 | Yes |  | Application
414 |  | DP-CRF-5384 | DP-CRF-5384-V1-WIN-AS | Dinesh | On-Going | On-Going | 1 | 2026-02-05 | 2026-02-05 | 0 | Yes |  | Application
415 |  |  | DP-CRF-5384-V1-WIN-LIBS |  | On-Going | On-Going | 1 | 2026-02-05 | 2026-02-05 | 0 | Yes |  | Application
416 |  | DP-VPX-2615 | DP-VPX-2615 | Jai ganesh | On-Going | On-Going | 7 | 2025-12-22 | 2026-02-11 | 51 | Yes |  | Application
417 |  |  | DP-VPX-2615-V1-01-LIBS-X64-W10 |  | On-Going | On-Going | 3 | 2025-12-22 | 2026-01-02 | 11 | Yes |  | Application
418 | YIA2652 | DP-CRF-8072 | DP-RFSS-8072-V1-WINS-AS | Abisheck | On-Hold | On-Hold | 3 | 2025-10-31 | 2025-11-11 | 11 | Yes |  | Application
419 |  |  | DP-RFSS-8072-V1-WNS-LIBS |  | On-Hold | On-Hold | 3 | 2025-10-31 | 2025-11-11 | 11 | Yes |  | Application
420 | YIA2927 | DP-SPL-5389 | DP-SPL-5389-V1-WIN-AS | Poornima | On-Going | On-Going | 17 | 2025-12-09 | 2026-02-11 | 64 | Yes |  | Application
421 |  |  | DP-SPL-5389-V1-WIN-LIBS |  | On-Going | On-Going | 13 | 2025-12-09 | 2026-01-29 | 51 | Yes |  | Application
422 | YEA2885 | DP-CRF-7391 | DP-SPL-7391-V1-AS-X64-W10 | Shivaram | Completed | Completed | 58 | 2024-12-19 | 2025-12-08 | 354 | Yes |  | Application
423 | YEA2885 | DP-BFU-8002 | DP-BFU-8002-603-V1-AS-X64-W10 | Shivaram | Completed | Completed | 101 | 2025-03-11 | 2026-02-10 | 336 | Yes |  | Application
424 |  |  | DP-BFU-8002-603-V1-LIBS-X64-W10 |  | Completed | Completed | 13 | 2025-03-11 | 2026-01-28 | 323 | Yes |  | Application
425 | YEA2885 | DP-SPL-1009 | DP-SPL-1009-V1-01-AS-X64-W10 | Yogeswaran | Completed | Completed | 149 | 2025-01-10 | 2026-01-07 | 362 | Yes |  | Application
426 |  |  | DP-SPL-1009-V1-01-LIBS-X64-W10 |  | Completed | Completed | 102 | 2025-01-10 | 2026-01-07 | 362 | Yes |  | Application
427 | YEA2885 | DP-SPL-7201 | DP-SPL-7201-V1-02-AS-X64-W10 | Arunkumar | Completed | Completed | 3 | 2025-01-07 | 2025-02-13 | 37 | Yes |  | Application
428 |  |  | DP-SPL-7201-V1-02-LIBS-X64-W10 |  | Completed | Completed | 17 | 2025-01-07 | 2025-09-16 | 252 | Yes |  | Application
429 | YEA2885 | DP-TRG-8184 | DP-TRG-8184-V1-02-AS-X64-W10 | Venkatesh | Completed | Completed | 58 | 2025-01-16 | 2026-01-31 | 380 | Yes |  | Application
430 | YEA2930 | DP-TRG-8226 | DP-TRG-8226-V1-01-AS-X64-W10 | Shivaram | On-Going | On-Going | 31 | 2026-01-03 | 2026-02-11 | 39 | Yes |  | Application
431 | YEA2930 | DP-ATE-8498 | DP-ATE-8498-V1-01-AS-X64-W10 | Krishnakumar | Completed | Completed | 80 | 2025-11-14 | 2026-02-11 | 89 | Yes |  | Application
432 | YEA2930 | DP-SSPA-5148 | DP-SSPA-5148-V1-02-AS-X64-W10 | Sasikumar | On-Going | On-Going | 2 | 2026-02-09 | 2026-02-12 | 3 | Yes |  | Application
433 | Common Utilities | Parameter Definer | DP-SDG-CMN-V1-US-PARAMDEF-X64-W10 | Shivaram | On-Going | On-Going | 9 | 2025-09-19 | 2025-12-05 | 77 | Yes |  | Application
434 | Common Utilities | Configuration Definer | DP-SDG-CMN-V1-US-CFGDEF-X64-W10 | Shivaram | On-Going | On-Going | 5 | 2025-09-19 | 2025-12-03 | 75 | Yes |  | Application
435 | Common Utilities | Template Application | DP-SDG-CMN-V1-AS-TEMPLATE-X64-W10 | Shivaram | On-Going | On-Going | 12 | 2025-09-19 | 2026-01-19 | 122 | Yes |  | Application
436 | Common Utilities | PDN Config Definer | DP-SDG-CMN-AS-PDNAUTOCONFIG-X64-W10 | Shivaram | On-Going | On-Going | 3 | 2025-12-19 | 2025-12-23 | 4 | Yes |  | Application
437 | Common Utilities | Power Supply Monitoring | DP-SDG-CMN-V1-AS-VM-X64-W10 | Shivaram | On-Going | On-Going | 10 | 2025-10-29 | 2026-02-12 | 106 | Yes |  | Application
438 | Common Utilities | Power Supply Plugin | DP-SDG-CMN-V1-LIBS-PS-X64-W10 | Shivaram | On-Going | On-Going | 25 | 2025-10-16 | 2025-11-27 | 42 | Yes |  | Application
439 | Common Utilities | DMM Automation | Dp-SDG-CMN-V1-AS-IMP-X64-W10 | Veeramainthan | On-Going | On-Going | 2 | 2025-10-28 | 2025-10-28 | 0 | Yes |  | Application
440 | Common Utilities | Report Generator | DP-SDG-CMN-V1-US-RPTGEN-DATE-X64-W10 | Arunkumar | On-Going | On-Going | 3 | 2025-09-23 | 2025-12-19 | 87 | Yes |  | Application
441 |  |  | DP-SDG-CMN-V1-US-RPTGEN-X64-W10 |  | On-Going | On-Going | 4 | 2025-09-19 | 2025-12-19 | 91 | Yes |  | Application
442 |  |  | DP-SDG-CMN-V1-US-RPTVIEW-X64-W10 |  | On-Going | On-Going | 11 | 2025-10-31 | 2025-12-12 | 42 | Yes |  | Application
443 | Common Utilities | Network analyzer | DP-SDG-CMN-V1-AS-NA-x64-W10 | Jai ganesh | On-Going | On-Going | 24 | 2025-10-13 | 2025-12-23 | 71 | Yes |  | Application
444 | Common Utilities | Servo App | DP-SDG-CMN-V1-US-ANTSERVO-X86-W10 | Krishnakumar | On-Going | On-Going | 4 | 2025-11-05 | 2025-11-05 | 0 | Yes |  | Application
445 | BEC2801 | DP-VPX-5846 | DP-VPX-5846-V2-APPS-X86-W10 | Krishnakumar | Completed | Completed | 14 | 2025-01-24 | 2025-10-01 | 250 | Yes |  | Application
446 | BEC2801 | DP-VPX-5846 | DP-VPX-5846-V2-LIBS-X86-W10 | Krishnakumar | Completed | Completed | 7 | 2025-01-24 | 2025-10-01 | 250 | Yes |  | Application
447 | YEB2935 | DP-ECM-1071 | DP-ECM-1071-V1-02-AS-X86-W10 | Krishnakumar | Completed | Completed | 24 | 2025-08-12 | 2025-12-01 | 111 | Yes |  | Application
448 | YEB2935 | DP-ECM-1071 | DP-ECM-1071-V1-02-AS-RPTTEMP-X86-W10 | Krishnakumar | Completed | Completed | 3 | 2025-09-26 | 2025-10-28 | 32 | Yes |  | Application
449 | YEB2935 | DP-ECM-1074 | DP-ECM-1074-V1-02-AS-X86-W10 | Krishnakumar | On-Hold | On-Hold | 4 | 2025-10-28 | 2025-10-30 | 2 | Yes |  | Application
450 |  | DP-ESM-1212 | DP-ESM-1212-V1-02-AS-X86-W10 | Parthipan | Completed | Completed | 30 | 2025-09-11 | 2025-12-05 | 85 | Yes |  | Application
451 |  |  | DP-ESM-1212-V1-02-AS-RPTTEMP-X86-W10 |  | Completed | Completed | 4 | 2025-09-26 | 2025-11-18 | 53 | Yes |  | Application
452 | YIC2814 | DP-CRF-7286 | DP-CRF-7286-V1-AS-X64-W10 | Arunkumar | Completed | Completed | 16 | 2025-02-18 | 2025-11-21 | 276 | Yes |  | Application
453 |  |  | DP-CRF-7286-V1-LIBS-X64-W10 |  | Completed | Completed | 13 | 2025-02-18 | 2025-11-21 | 276 | Yes |  | Application
454 |  | DP-CRF-7289 | DP-CRF-7289-V1-AS-X64-W10 |  | On-Hold | On-Hold | 5 | 2025-06-12 | 2026-01-27 | 229 | Yes |  | Application
455 | YIC2814 |  | DP-CRF-7289-V1-LIBS-X64-W10 | Arunkumar | On-Hold | On-Hold | 5 | 2025-06-12 | 2026-01-27 | 229 | Yes |  | Application
456 | YEB2992 | DP-CHT-003-3960384 | DP-CHT-003-3960384-V1-AS-LT-X86-W10 | Arunkumar | On-Hold | On-Hold | 22 | 2025-09-03 | 2025-12-18 | 106 | Yes |  | Application
457 |  |  | DP-CHT-003-3960384-V1-AS-APPINFO-X86-W10 |  | On-Hold | On-Hold | 2 | 2025-09-03 | 2025-09-04 | 1 | Yes |  | Application
458 |  |  | DP-CHT-003-3960384-V1-AS-HARNESSMERGE-X86-W10 |  | On-Hold | On-Hold | 8 | 2025-11-14 | 2025-12-31 | 47 | Yes |  | Application
459 | YEA2936 | DP-CRF-6654 | DP-CRF-6654-V1-AS-X64-COS7 | Yogeswaran | On-Hold | On-Hold | 7 | 2025-09-05 | 2025-12-11 | 97 | Yes |  | Application
460 |  |  | DP-CRF-6654-V1-LIBS-X64-COS7 |  | On-Hold | On-Hold | 1 | 2025-09-05 | 2025-09-05 | 0 | Yes |  | Application
461 | YIA2909 | DP-SPL-5374 | DP-SPL-5374-V1-01-AS-X64-W10-1V00 | Sasikumar |  |  | 20 | 2025-05-15 | 2025-07-15 | 61 | Yes |  | Application
462 |  |  | DP-SPL-5374-V1-01-LIBS-X64-W10-1V00 |  |  |  | 17 | 2025-05-15 | 2025-07-15 | 61 | Yes |  | Application
463 | YIA2909 | DP-SSPA-5148 | DP-SSPA-5148-V1-01-AS-X64-W10 | Sasikumar | On-Hold | On-Hold | 27 | 2025-07-01 | 2026-01-20 | 203 | Yes |  | Application
464 |  |  | DP-SSPA-5148-V1-01-LIBS-X64-W10 |  | On-Hold | On-Hold | 8 | 2025-07-01 | 2025-12-26 | 178 | Yes |  | Application
465 | YEC2826 | DP-SPL-7120-600 | DP-SPL-7120-V1-01-AS-X64-W10-1V00 |  | On-Going | On-Going | 10 | 2025-10-28 | 2026-02-09 | 104 | Yes |  | Application
466 |  |  | DP-7120-5374-V1-01-LIBS-X64-W10-1V00 | Sasikumar | On-Going | On-Going | 8 | 2025-10-28 | 2026-02-09 | 104 | Yes |  | Application
467 | YEC2934 | DP-RFSS-7121-669 | DP-RFSS-7121-669-V1-01-AS-X64-W10 | Jai ganesh | Completed | Completed | 49 | 2025-01-20 | 2025-04-21 | 91 | Yes |  | Application
468 |  |  | DP-RFSS-7121-669-V1-01-LIBS-X64-W10 |  | Completed | Completed | 16 | 2025-01-20 | 2025-03-25 | 64 | Yes |  | Application
469 | YIC2814 | DP-CRF-7292 | DP-CRF-7292-V1-01-AS-X64-W10 | Naveenkumar | On-Going | On-Going | 25 | 2025-06-02 | 2026-02-03 | 246 | Yes |  | Application
470 | YIC2814 | DP-RFSS-7724 | DP-RFSS-7724-V1-01-AS-X64-W10 | Naveenkumar | On-Going | On-Going | 1 | 2025-09-05 | 2025-09-05 | 0 | Yes |  | Application
471 |  |  | DP-RFSS-7724-V1-01-LIBS-X64-W10 |  | On-Going | On-Going | 2 | 2026-01-20 | 2026-01-21 | 1 | Yes |  | Application
472 | YIC2814 | DP-RFSS-7721 | DP-RFSS-7721-V1-01-AS-X64-W10 | Naveenkumar | On-Hold | On-Hold | 11 | 2025-05-09 | 2026-01-20 | 256 | Yes |  | Application
473 | YEB2989 | DP-CRF-0512 | DP-CRF-0512-V1-01-AS-X64-W10 | Naveenkumar |  |  | 6 | 2025-11-21 | 2025-12-24 | 33 | Yes |  | Application
474 |  |  | DP-CRF-0512-V1-01-LIBS-X64-W10 |  |  |  | 3 | 2025-11-21 | 2025-12-10 | 19 | Yes |  | Application
475 | sia2928_manet |  | Test |  | Current | Current | 14 | 2025-06-18 | 2025-11-07 | 142 | Yes |  | BSP
476 | sia2928_sdr_sca |  | SCA-QPSK-100KBPS |  | Current | Current | 26 | 2025-09-05 | 2026-01-13 | 130 | Yes |  | BSP
477 | yeb2986_mmdc | DP-OBC-8205 | DP-OBC-8205-V1-01-AS-HOST-X86_64-W10 |  | Current | Current | 17 | 2025-06-20 | 2025-12-15 | 178 | Yes |  | BSP
478 | yeb2986_mmdc | DP-OBC-8205 | DP-OBC-8205-V1-01-AS-TARGET-X86_64-VxW7 |  | Current | Current | 22 | 2025-08-13 | 2026-01-24 | 164 | Yes |  | BSP
479 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-ATP-SRC |  | Current | Current | 3 | 2025-12-23 | 2025-12-24 | 1 | Yes |  | BSP
480 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-DRV-SRC |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
481 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-LIB-SRC |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
482 | yeb2995_fcs-ngmmcb |  | CENTOS10-OFFICIAL-ISO |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
483 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-CUSTOM-ISO |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
484 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-KERNEL-CONFIG-FILE |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
485 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-KERNEL-SRC |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
486 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-XENO-LIB-SRC |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
487 | yeb2995_fcs-ngmmcb | DP-VME-0669 | DP-VME-0669-BRD-XENO-PATCH-FILE |  | Current | Current | 1 | 2025-12-23 | 2025-12-23 | 0 | Yes |  | BSP
488 | yec2708_newgenairsdr | DP-COMM-8031 | DP-COMM-8031-V1-AS-ALGO-ARM-LIN64 |  | On hold | On hold | 14 | 2025-09-23 | 2026-01-27 | 126 | Yes |  | BSP
489 | yec2708_newgenairsdr | DP-COMM-8031 | DP-COMM-8031-V1-AS-AUDIO-ARM-LIN64 |  | On hold | On hold | 19 | 2025-09-18 | 2026-01-27 | 131 | Yes |  | BSP
490 | yec2708_newgenairsdr | DP-COMM-8031 | DP-COMM-8031-V1-AS-HOST-x86-W10 |  | On hold | On hold | 78 | 2025-08-11 | 2026-02-12 | 185 | Yes |  | BSP
491 | yec2708_newgenairsdr | DP-COMM-8031 | DP-COMM-8031-V1-AS-SIGNAL-ARM-LIN64 |  | On hold | On hold | 17 | 2025-09-23 | 2026-01-27 | 126 | Yes |  | BSP
492 | yec2877-ucr | DP-COMM-8079 | DP-COMM-8079-V1-AS-AUDIO-ARM-LIN64 |  | Stopped | Stopped | 4 | 2025-07-03 | 2025-10-24 | 113 | Yes |  | BSP
493 | yec2877-ucr | DP-COMM-8079 | DP-COMM-8079-V1-AS-X86-WIN |  | Stopped | Stopped | 14 | 2025-07-03 | 2025-08-12 | 40 | Yes |  | BSP
494 | yec2877-ucr | DP-COMM-8079 | DP-COMM-8079-V1-FWS-SECURITY |  | Stopped | Stopped | 3 | 2025-07-03 | 2025-10-24 | 113 | Yes |  | BSP
495 | yec2877-ucr | DP-COMM-8079 | DP-COMM-8079-V1-FWS-SIGNAL |  | Stopped | Stopped | 3 | 2025-07-03 | 2025-10-24 | 113 | Yes |  | BSP
496 | yec2877-ucr | DP-COMM-8079 | DP-COMM-8079-V1-FWS-CYPRESS |  | Stopped | Stopped | 1 | 2025-06-13 | 2025-06-13 | 0 | Yes |  | BSP
497 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-AS-SYS-ATP-AUDIO-ARM-LIN64 |  | Current | Current | 5 | 2026-02-12 | 2026-02-12 | 0 | Yes |  | BSP
498 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-AS-SYS-ATP-SEC-ARM-LIN64 |  | Current | Current | 3 | 2026-02-12 | 2026-02-12 | 0 | Yes |  | BSP
499 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-AS-SYS-ATP-SIGNAL-ARM-LIN64 |  | Current | Current | 3 | 2026-02-12 | 2026-02-12 | 0 | Yes |  | BSP
500 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-AS-AUDIO-ARM-LIN64 |  | Current | Current | 1 | 2025-09-17 | 2025-12-26 | 100 | Yes |  | BSP
501 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-AS-AUDIO-ARM-LIN64 |  | Current | Current | 30 | 2025-09-17 | 2025-12-26 | 100 | Yes |  | BSP
502 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-FWS-SECURITY |  | Current | Current | 3 | 2025-12-26 | 2025-12-29 | 3 | Yes |  | BSP
503 | yib2156_manpack_sdr | DP-COMM-8022 | DP-COMM-8022-V1-FWS-SIGNAL |  | Current | Current | 3 | 2025-12-02 | 2025-12-26 | 24 | Yes |  | BSP
504 | yib2156_manpack_sdr |  | project_sample |  | Current | Current | 1 | 2026-01-21 | 2026-01-21 | 0 | Yes |  | BSP
505 | yic2835_small_ff_sdr | DP-COMM-8076 | DP-COMM-8076-V1-AS-HOST-x86-W10 |  | Current | Current | 10 | 2025-08-11 | 2026-01-01 | 143 | Yes |  | BSP
506 | yic2835_small_ff_sdr |  | DP-COMM-8076-V1-AS-SIGNAL-ARM-LIN64 |  | On hold | On hold | 24 | 2025-08-21 | 2026-01-27 | 159 | Yes |  | BSP
507 | yic2964-aeecu | DP-OBC-1014 | DP-OBC-1014-V1-01-LIBS-ARM-FW-WITH-MISRA |  | Current | Current | 41 | 2025-09-01 | 2026-02-05 | 157 | Yes |  | BSP
508 | yic2964-aeecu | DP-OBC-1014 | DP-OBC-1014-V1-01-LIBS-ARM-FW-WITHOUT-MISRA |  | On hold | On hold | 25 | 2025-08-13 | 2025-08-25 | 12 | Yes |  | BSP
509 | yea2885_agru_ate |  | AS |  | Completed | Completed | 1 | 2024-12-18 | 2024-12-18 | 0 | Yes |  | BSP
510 | yea2885_agru_ate |  | DS |  | Completed | Completed | 3 | 2024-12-18 | 2024-12-19 | 1 | Yes |  | BSP
511 | yeb2986_mmdc | DP-VPX-3611 | DP-VPX-3611-V1-AS-X86-W10 |  | Current | Current | 1 | 2025-12-09 | 2025-12-09 | 0 | Yes |  | BSP
512 | yeb2986_mmdc |  | DP-VPX-3611-V1-AS |  | Current | Current | 1 | 2025-07-02 | 2025-07-02 | 0 | Yes |  | BSP
513 | yeb2986_mmdc |  | DP-VPX-3611-V1-DS |  | Current | Current | 7 | 2025-07-02 | 2026-02-12 | 225 | Yes |  | BSP
514 | yeb2986_mmdc |  | DRV |  | Current | Current | 5 | 2025-10-06 | 2026-01-24 | 110 | Yes |  | BSP
515 | yic2964-aeecu |  | ATE-QT-TARGET |  | On hold | On hold | 3 | 2025-10-31 | 2025-11-01 | 1 | Yes |  | BSP
516 | yic2964-aeecu |  | ATE-HOST |  | On hold | On hold | 9 | 2025-10-31 | 2025-11-27 | 27 | Yes |  | BSP
517 | yic2964-aeecu |  | QT-HOST |  | On hold | On hold | 6 | 2025-11-27 | 2025-11-27 | 0 | Yes |  | BSP
518 | YIA2822 | DP-VPX-0972 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
519 |  | DP-VPX-0701 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
520 | BIA2525 | DP-SPL-4021 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
521 | YEB2763 | DP-OBC-8103 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
522 |  | DP-OBC-0453 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
523 |  | DP-OBC-5118 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
524 | YIB2821 | DP-COMM-8031 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
525 | YIC2105 | DP-SPL-0124 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
526 | YEB2848 | DP-OBC-8163 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
527 | YEA2864 | DP-XMC-5775 |  |  | Completed | Completed | 0 |  |  | 0 | No |  | BSP
528 | YIB2815 | DP-VPX-3608 |  |  | Completed | Completed | 0 |  |  | 0 | No |  | BSP
529 | YIC2823 | DP-SPL-4039 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
530 | YEA2930 | DP-VPX-1028 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
531 |  | DP-VPX-5294 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
532 | YEA2846 | DP-VPX-1025 |  |  | Completed | Completed | 0 |  |  | 0 | No |  | BSP
533 | BIA2896 | DP-SPL-3511 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
534 | YEB2986 | DP-VPX-0930 |  |  | On hold | On hold | 0 |  |  | 0 | No |  | BSP
535 |  | DP-OBC-8205 |  |  | On hold | On hold | 0 |  |  | 0 | No |  | BSP
536 | SIA2928 | SCA |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
537 | YEC2708 | DP-COMM-8031 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
538 | YIA2822 | DP-VPX-0972 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
539 |  | DP-VPX-0701 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
540 |  | DP-XMC-5046 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
541 |  | DP-XMC-5007 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
542 |  | DP-XMC-6000 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
543 |  | DP-XMC-5010 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
544 |  | DP-SPL-4507 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
545 | YEB2995 | DP-VME-0669 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP
546 |  | DP-XMC-5535 |  |  | Current | Current | 0 |  |  | 0 | No |  | BSP

## Team Details
TEAM-WISE DETAILED GIT AUDIT
Team | Total CIs | Git Avail. | Git N/A | Adoption % | Completed | In Progress | On Hold | Total Pushes | Unique Products
AGM | 71 | 55 | 16 | 77.5% | 4 | 10 | 1 | 283 | 30
Application | 217 | 182 | 35 | 83.9% | 84 | 72 | 16 | 2710 | 90
BSP | 72 | 43 | 29 | 59.7% | 5 | 51 | 11 | 428 | 31
Computing | 99 | 92 | 7 | 92.9% | 4 | 14 | 2 | 506 | 25
RAD | 86 | 73 | 13 | 84.9% | 13 | 8 | 10 | 1305 | 25

## Product Status
PRODUCT-WISE GIT AVAILABILITY
Team | Product ID | Git Available | Git Not Avail. | Total CIs | Adoption %
AGM | DP-COM-8031-630 | 1 | 0 | 1 | 100.0%
AGM | DP-COM-8031-633 | 1 | 0 | 1 | 100.0%
AGM | DP-CRF-2213 | 1 | 0 | 1 | 100.0%
AGM | DP-CRF-2519 | 1 | 0 | 1 | 100.0%
AGM | DP-CRF-5366 | 1 | 0 | 1 | 100.0%
AGM | DP-CRF-5369 | 1 | 0 | 1 | 100.0%
AGM | DP-CRF-7556 PLL | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1073-6333-HF-RPE | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1074-6000-VUSHF-RPE | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1095-600-AIDF | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1095-603-MIDF | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1098-600-CFDF | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1098-603-MRA | 1 | 0 | 1 | 100.0%
AGM | DP-ESM-1212-6033-VUSHF-Mrx | 1 | 0 | 1 | 100.0%
AGM | DP-EW-8002-630 | 1 | 0 | 1 | 100.0%
AGM | DP-EW-8002-699 | 1 | 0 | 1 | 100.0%
AGM | DP-PSU-7357 | 1 | 0 | 1 | 100.0%
AGM | DP-PSU-8287 | 0 | 1 | 1 | 0.0%
AGM | DP-RDR-8314 | 1 | 0 | 1 | 100.0%
AGM | DP-ROM-8036 | 1 | 0 | 1 | 100.0%
AGM | DP-SPL-4003 | 1 | 0 | 1 | 100.0%
AGM | DP-SPL-5452 | 1 | 0 | 1 | 100.0%
AGM | DP-SPL-6735 | 1 | 0 | 1 | 100.0%
AGM | DP-SPL-7123 | 0 | 1 | 1 | 0.0%
AGM | DP-SPL-7183 | 1 | 0 | 1 | 100.0%
AGM | DP-SPL-7306 | 0 | 1 | 1 | 0.0%
AGM | DP-TRM-8030 | 0 | 1 | 1 | 0.0%
AGM | IT-SPL-5000 | 1 | 0 | 1 | 100.0%
AGM | IT-SPL-5003 | 1 | 0 | 1 | 100.0%
Application | Configuration Definer | 1 | 0 | 1 | 100.0%
Application | DMM Automation | 1 | 0 | 1 | 100.0%
Application | DP-ANT-7094 | 1 | 0 | 1 | 100.0%
Application | DP-ATE-8210 | 0 | 2 | 2 | 0.0%
Application | DP-ATE-8420 | 1 | 0 | 1 | 100.0%
Application | DP-ATE-8423 | 1 | 0 | 1 | 100.0%
Application | DP-ATE-8456 | 2 | 0 | 2 | 100.0%
Application | DP-ATE-8483 | 3 | 0 | 3 | 100.0%
Application | DP-ATE-8489 | 0 | 1 | 1 | 0.0%
Application | DP-ATE-8498 | 1 | 0 | 1 | 100.0%
Application | DP-BFU-8002 | 1 | 0 | 1 | 100.0%
Application | DP-CHT-003-3960384 | 1 | 0 | 1 | 100.0%
Application | DP-COMM-8037 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-0512 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-5273 | 0 | 1 | 1 | 0.0%
Application | DP-CRF-5325 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-5381 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-5384 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-6308 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-6398 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-6419 | 1 | 1 | 2 | 50.0%
Application | DP-CRF-6654 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7286 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7289 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7292 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7316 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7391 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7457 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7457-663 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7463 | 0 | 1 | 1 | 0.0%
Application | DP-CRF-7544 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-7553 | 1 | 0 | 1 | 100.0%
Application | DP-CRF-8072 | 1 | 0 | 1 | 100.0%
Application | DP-DMCS-8125 | 0 | 1 | 1 | 0.0%
Application | DP-DRM-8008 | 0 | 1 | 1 | 0.0%
Application | DP-DRM-8011 | 1 | 0 | 1 | 100.0%
Application | DP-DTM-8003 | 0 | 1 | 1 | 0.0%
Application | DP-DTRM-8019 | 1 | 0 | 1 | 100.0%
Application | DP-ECM-1071 | 2 | 0 | 2 | 100.0%
Application | DP-ECM-1074 | 2 | 0 | 2 | 100.0%
Application | DP-ECM-1215 | 1 | 0 | 1 | 100.0%
Application | DP-ESM-1062 | 0 | 1 | 1 | 0.0%
Application | DP-ESM-1212 | 1 | 0 | 1 | 100.0%
Application | DP-EW-8002 | 1 | 0 | 1 | 100.0%
Application | DP-EW-8014 | 1 | 0 | 1 | 100.0%
Application | DP-OBC-1149 | 1 | 0 | 1 | 100.0%
Application | DP-OBC-3012 | 1 | 0 | 1 | 100.0%
Application | DP-OBC-5028 | 1 | 0 | 1 | 100.0%
Application | DP-OBC-8178 | 2 | 0 | 2 | 100.0%
Application | DP-OBC-8178-V1-02-US-LINUX | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8161 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8164 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8167 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8170 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8176 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8179 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8182 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8185 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8188 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8191 | 1 | 0 | 1 | 100.0%
Application | DP-RDR-8335 | 0 | 2 | 2 | 0.0%
Application | DP-RFSS-7121-669 | 1 | 0 | 1 | 100.0%
Application | DP-RFSS-7142 | 1 | 0 | 1 | 100.0%
Application | DP-RFSS-7145 | 1 | 0 | 1 | 100.0%
Application | DP-RFSS-7148 | 1 | 0 | 1 | 100.0%
Application | DP-RFSS-7721 | 1 | 0 | 1 | 100.0%
Application | DP-RFSS-7724 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-1009 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-5374 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-5389 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-6907 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-7120-600 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-7153 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-7180 | 1 | 0 | 1 | 100.0%
Application | DP-SPL-7201 | 1 | 0 | 1 | 100.0%
Application | DP-SPU-8019 | 1 | 0 | 1 | 100.0%
Application | DP-SSPA-5148 | 2 | 0 | 2 | 100.0%
Application | DP-TMC-8148 | 0 | 1 | 1 | 0.0%
Application | DP-TRG-8184 | 1 | 0 | 1 | 100.0%
Application | DP-TRG-8226 | 1 | 0 | 1 | 100.0%
Application | DP-VPX-2615 | 1 | 0 | 1 | 100.0%
Application | DP-VPX-5846 | 2 | 0 | 2 | 100.0%
Application | Network analyzer | 1 | 0 | 1 | 100.0%
Application | PDN Config Definer | 1 | 0 | 1 | 100.0%
Application | Parameter Definer | 1 | 0 | 1 | 100.0%
Application | Power Supply Monitoring | 1 | 0 | 1 | 100.0%
Application | Power Supply Plugin | 1 | 0 | 1 | 100.0%
Application | Report Generator | 1 | 0 | 1 | 100.0%
Application | Servo App | 1 | 0 | 1 | 100.0%
Application | Template Application | 1 | 0 | 1 | 100.0%
BSP | DP-COMM-8022 | 7 | 0 | 7 | 100.0%
BSP | DP-COMM-8031 | 4 | 2 | 6 | 66.7%
BSP | DP-COMM-8076 | 1 | 0 | 1 | 100.0%
BSP | DP-COMM-8079 | 5 | 0 | 5 | 100.0%
BSP | DP-OBC-0453 | 0 | 1 | 1 | 0.0%
BSP | DP-OBC-1014 | 2 | 0 | 2 | 100.0%
BSP | DP-OBC-5118 | 0 | 1 | 1 | 0.0%
BSP | DP-OBC-8103 | 0 | 1 | 1 | 0.0%
BSP | DP-OBC-8163 | 0 | 1 | 1 | 0.0%
BSP | DP-OBC-8205 | 2 | 1 | 3 | 66.7%
BSP | DP-SPL-0124 | 0 | 1 | 1 | 0.0%
BSP | DP-SPL-3511 | 0 | 1 | 1 | 0.0%
BSP | DP-SPL-4021 | 0 | 1 | 1 | 0.0%
BSP | DP-SPL-4039 | 0 | 1 | 1 | 0.0%
BSP | DP-SPL-4507 | 0 | 1 | 1 | 0.0%
BSP | DP-VME-0669 | 8 | 1 | 9 | 88.9%
BSP | DP-VPX-0701 | 0 | 2 | 2 | 0.0%
BSP | DP-VPX-0930 | 0 | 1 | 1 | 0.0%
BSP | DP-VPX-0972 | 0 | 2 | 2 | 0.0%
BSP | DP-VPX-1025 | 0 | 1 | 1 | 0.0%
BSP | DP-VPX-1028 | 0 | 1 | 1 | 0.0%
BSP | DP-VPX-3608 | 0 | 1 | 1 | 0.0%
BSP | DP-VPX-3611 | 2 | 0 | 2 | 100.0%
BSP | DP-VPX-5294 | 0 | 1 | 1 | 0.0%
BSP | DP-XMC-5007 | 0 | 1 | 1 | 0.0%
BSP | DP-XMC-5010 | 0 | 1 | 1 | 0.0%
BSP | DP-XMC-5046 | 0 | 1 | 1 | 0.0%
BSP | DP-XMC-5535 | 0 | 1 | 1 | 0.0%
BSP | DP-XMC-5775 | 0 | 1 | 1 | 0.0%
BSP | DP-XMC-6000 | 0 | 1 | 1 | 0.0%
BSP | SCA | 0 | 1 | 1 | 0.0%
Computing | DP-ATE-8486 | 0 | 1 | 1 | 0.0%
Computing | DP-DSP-8208 | 1 | 0 | 1 | 100.0%
Computing | DP-OBC-8196 | 1 | 0 | 1 | 100.0%
Computing | DP-OBC-8211 | 0 | 1 | 1 | 0.0%
Computing | DP-SPL-0238 | 1 | 0 | 1 | 100.0%
Computing | DP-SPL-0241 | 0 | 1 | 1 | 0.0%
Computing | DP-SPL-0244 | 1 | 0 | 1 | 100.0%
Computing | DP-SPL-0502 | 0 | 1 | 1 | 0.0%
Computing | DP-SPL-4309 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-0224 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-0227 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-0233 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-0236 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-0500 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-1031 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-2003 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-2606 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-5291 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-5792 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-6025 | 1 | 0 | 1 | 100.0%
Computing | DP-VPX-7154 | 1 | 0 | 1 | 100.0%
Computing | DP-XMC-5049 | 1 | 0 | 1 | 100.0%
Computing | DP-XMC-6003 | 0 | 1 | 1 | 0.0%
Computing | IRST V2 | 0 | 1 | 1 | 0.0%
RAD | DP-ADSB-8009 | 1 | 0 | 1 | 100.0%
RAD | DP-ATE-8432 | 0 | 1 | 1 | 0.0%
RAD | DP-IFF-8023 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-7277 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-7310 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-7388 | 0 | 1 | 1 | 0.0%
RAD | DP-RDR-7456 | 0 | 1 | 1 | 0.0%
RAD | DP-RDR-7465 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-7474 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-7477 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-7495 | 0 | 1 | 1 | 0.0%
RAD | DP-RDR-7570 | 0 | 1 | 1 | 0.0%
RAD | DP-RDR-8134 | 2 | 0 | 2 | 100.0%
RAD | DP-RDR-8140 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-8227 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-8245 | 1 | 0 | 1 | 100.0%
RAD | DP-RDR-8266 | 0 | 1 | 1 | 0.0%
RAD | DP-RDR-8308 | 0 | 1 | 1 | 0.0%
RAD | DP-RDR-8329 | 0 | 1 | 1 | 0.0%
RAD | DP-RTS-8006 | 1 | 0 | 1 | 100.0%
RAD | DP-SAR-8004 | 0 | 1 | 1 | 0.0%
RAD | DP-SAR-8007 | 0 | 1 | 1 | 0.0%
RAD | DP-SWR-8002 | 1 | 0 | 1 | 100.0%
RAD | DP-SWR-8005 | 1 | 0 | 1 | 100.0%

## Legend & Notes
LEGEND & NOTES
COLOR CODING
Green background | Git adoption >= 80%
Yellow background | Git adoption 50–79%
Red background | Git adoption < 50%
Navy header | Section/column header
Teal header | Data table header
TEAM CODES
Computing | Computing / Embedded team
AGM | AGM team
Application | Application software team
BSP | Board Support Package team
RAD | RAD / Radar systems team
GIT AVAILABILITY
Available / Yes | CI is tracked in Git
Not Available / No | CI is not in Git (action needed)